## TDD Tracker
S.No. | S.No.2 | Sub-Module / Process | Task / Development Description | Requirement / TDD Ref. | Priority | Owner / Developer | Overall Status | Development Status | Development Completion Date | 1st Level Testing Status | 1st Level Testing Completed Date | 1st Level Tester | 1st Level Remarks / Defect Ref. | 2nd Level Testing Status | 2nd Level Testing Completed Date | 2nd Level Tester | 2nd Level Remarks / Defect Ref. | 3rd Level Testing Status | 3rd Level Testing Completed Date | 3rd Level Tester | 3rd Level Remarks / UAT Ref. | Final Testing Completion Date | Go-Live Ready | Remarks / Dependency
1 | Admin | Change Log | Change log activation should be managed through the set user, and should have the provision to activate the specific table under the change log, User-ID wise and function wise. Any record (changes/modification) within the application must be provided with date and time with old record and new record. |  |  |  | Not Started | [15 empty] | No
2 | Admin | Multi-Language | Multi-lingual access of the application at dashboard and application login
3 | Admin | NOB=Livestock ( Ex- AGRICULTURE, POULTRY, LIVESTOCK) | Universal NOBs should be present |  |  |  | Not Started | [15 empty] | No
4 | Admin | LOB=Piggery | LOB should be provided as per the selected NOB |  |  |  | Not Started | [15 empty] | No
5 |  |  | Animal Register should show a LIST PAGE of all Animals, CLICKABLE, to further show each ANIMAL's CARD to get ANIMAL-SPECIFIC DATA and breeding details etc. There should also be an OVERVIEW pane (RHS)
6 | Masters | Animal Register Master | Animal Code per animal should be auto-generated in No. series (alphanumeric value) ex-PIG-YYYY-SEQ |  |  |  | Not Started | [15 empty] | No
7 | Masters | Animal Register Master | Animal type should be provided as sow/boar/gilt/piglet/commercial pig (as fetched according to the NOB/LOB) |  |  |  | Not Started | [15 empty] | No
8 | Masters | Animal Register Master | Animal Breed should be filtered according to the NOB (lookup from the breedmaster)
9 | Masters | Animal Register Master | Gender for every type of animal should show either Male or Female |  |  |  | Not Started | [15 empty] | No
10 | Masters | Animal Register Master | DOB for each animal should be entered if born on the farm or purchased( synced from business central) |  |  |  | Not Started | [15 empty] | No
11 | Masters | Animal Register Master | Age at entry week,should be auto computed as per DOB of BORN ON FARM animals and MANUAL ENTRY if animals are IMPORTED |  |  |  | Not Started | [15 empty] | No
12 | Masters | Animal Register Master | Entry type should show purchased local/purchased imported/transferred/born for further classification of the animal REGISTERED when Animals enter the Farm |  |  |  | Not Started | [15 empty] | No
13 | Masters | Animal Register Master | Entry date should indicate the exact date on which an animal was admitted to a particular farm (numeric/calander based) |  |  |  | Not Started | [15 empty] | No
14 | Masters | Animal Register Master | Source GRN should be alphanumeric, applicable only for PURCHASED animal type. |  |  |  | Not Started | [15 empty] | No
15 | Masters | Animal Register Master | SOURCE BATCH BORN FROM is applicable only for the animals classified as BORN ON FARM. It will indicate the previous farrowing batch for the animals BORN ON FARM, from which the animals are taken. |  |  |  | Not Started | [15 empty] | No
16 | Masters | Animal Register Master | Animal Item should be LOOKED UP from item master where the item type is categorised (linking INVENTORY & COSTING)
17 | Masters | Animal Register Master | SERIAL NO. for individual item of the lot be linked/fetched
18 | Masters | Animal Register Master | RFID, unique per animal(REGISTERED) which is scannable (for traceability) |  |  |  | Not Started | [15 empty] | No
19 | Masters | Animal Register Master | Ear tag number is unique for each animal (alphanumeric) |  |  |  | Not Started | [15 empty] | No
20 | Masters | Animal Register Master | Sire and Dam should be linked to the animal, being registered, for a better tracking of a specific progeny.(RECORD)
21 | Masters | Animal Register Master | Acquisition Cost(purchase price per animal), should be fetched from GRN (for PURCHASED animals only) and manual entry should be allowed on GRN for other non-purchased animals.
22 | Masters | Animal Register Master | Landing Cost, would be calculated/applicable for IMPORTED animals, kept in QUARANTINE ( transport cost+quarantine overhead charges)
23 | Masters | Animal Register Master | Total Opening Asset Value, at entry (AUTO-CALCULATED)
24 | Masters | Animal Register Master | Current Stage should show the stage at which this particular animal is at a particular location. It should include QUARANTINE / GILT_GROWER / FLUSH / DRY_SOW / GESTATION / FARROWING / WEANING / PRODUCTIVE_SOW / BOAR_AI / CULLED / DEAD / SOLD / SLAUGHTERED ( fetch from ANIMAL TYPE during entry at farm) |  |  |  | Not Started | [15 empty] | No
25 | Masters | Animal Register Master | Current active batch, should be fetched from the batch that particular animal is in (numerical) |  |  |  | Not Started | [15 empty] | No
26 | Masters | Animal Register Master | Current Location is fetched as per the particular animal is in a particular farm/pen location. |  |  |  | Not Started | [15 empty] | No
27 | Masters | Animal Register Master | Parity count refers to number of completed pregnancies of an animal, post weaning. It should be upto a two digit numeric value. It should carry series of 1. |  |  |  | Not Started | [15 empty] | No
28 | Masters | Animal Register Master | Total piglets born live should tell number of live piglets per farrowing over the lifetime (previous +current=cumulative total) It should be numeric value upto 3-4 digits |  |  |  | Not Started | [15 empty] | No
29 | Masters | Animal Register Master | Total piglets weaned should tell the number of piglets weaned over the lifetime. It should be a numeric value upto 3-4 digits |  |  |  | Not Started | [15 empty] | No
30 | Masters | Animal Register Master | Current Bio Asset Value, should be auto-updated from the ledger(BC)
31 | Masters | Animal Register Master | Total Amortised would flow from BC
32 | Masters | Animal Register Master | Book Value NBV
33 | Masters | Animal Register Master | Residual Value would flow from BC
34 | Masters | Animal Register Master | Monthly Amortisation, to be AUTO-CALCULATED (numeric with decimal)
35 | Masters | Animal Register Master | Productive Life Start Date should tell about the first farrowing date of a particular animal. It should be 8-digit numeric value or calander-based |  |  |  | Not Started | [15 empty] | No
36 | Masters | Animal Register Master | Expected cull date should be numeric value which will tell about the expected disposal date ( to be fetched as per PRODUCTIVE LIFE START DATE) |  |  |  | Not Started | [15 empty] | No
37 | Masters | Animal Register Master | Animal status should show ACTIVE / QUARANTINE / SICK / PREGNANT / LACTATING / DRY / CULLED / DEAD / SOLD / SLAUGHTERED (as per the ANIMAL STAGE) |  |  |  | Not Started | [15 empty] | No
38 | Masters | Animal Register Master | Disposal date should be a numeric value or based on calander. It is the date on which a particular batch is disposed on the basis of sale/slaughter/animal died.( applicable only only as per ANIMAL STATUS) |  |  |  | Not Started | [15 empty] | No
39 | Masters | Animal Register Master | Disposal type should show SOLD / SLAUGHTERED / DIED / TRANSFERRED |  |  |  | Not Started | [15 empty] | No
40 | Masters | Animal Register Master | Number of teats should be upto two digit numeric value ( would serve as an indicator of sow's productivity) |  |  |  | Not Started | [15 empty] | No
41 | Masters | Animal Register Master | TSI, would be provided by TOPIGS ( to be FETCHED from that)
42 | Masters | Animal Register Master | Grading, would be done by the company itself ( single digit NUMERIC value)
43 |  | Animal Register Master | Bio Asset Value, would flow from BC (sync/fetch)
44 | Masters | Breeding Record | Sow, being mated, should be looked up from ANIMAL REGISTER where animal type and other details should be provided . |  |  |  | Not Started | [15 empty] | No
45 | Masters | Breeding Record | Batch, to be linked where this process is taking place (Flushing/AI) (Animal Register) |  |  |  | Not Started | [15 empty] | No
46 | Masters | Breeding Record | Mating Type, should provide AI or Natural Mating |  |  |  | Not Started | [15 empty] | No
47 | Masters | Breeding Record | BOAR, should appear only if the mating type is NATURAL MATING |  |  |  | Not Started | [15 empty] | No
48 | Masters | Breeding Record | SEMEN LOT, should appear only if the mating type is AI ( to be consumed as FIFO) |  |  |  | Not Started | [15 empty] | No
49 | Masters | Breeding Record | Semen Dose Quantity, applicable for AI only (Numeric 2 digit value)(CONDITIONAL) |  |  |  | Not Started | [15 empty] | No
50 | Masters | Breeding Record | Mating Date, should be entered in numerical value/based on calander (for both AI/Natural mating) { NUMERIC VALUE} |  |  |  | Not Started | [15 empty] | No
51 | Masters | Breeding Record | Second Mating Date, should only be provided if the Mating type is AI (NUMERIC VALUE) and animal found im-pregnant post first AI SEMEN DOSE (within 48 HRS) |  |  |  | Not Started | [15 empty] | No
52 | Masters | Breeding Record | Expected Farrowing Date, should be auto-fetched using the mating date (NUMERIC VALUE) 116 Days |  |  |  | Not Started | [15 empty] | No
53 | Masters | Breeding Record | Pregnancy Check Date, should be a numerical value,applicable post-28 days of mating for both AI/NATURAL (DD/MM/YYYY) |  |  |  | Not Started | [15 empty] | No
54 | Masters | Breeding Record | Pregnancy Check Method should provide ULTRASOUND / RECTAL / VISUAL / NOT CHECKED (applicable for SOW only)
55 | Masters | Breeding Record | Pregnancy Confirmed, should provide pending/confirmed/fail (against SOWs only)
56 | Masters | Breeding Record | Conception Result should provide CONFIRMED / REPEAT / FAILED / PENDING ( for SOW bred only)
57 | Masters | Breeding Record | Parity Number should be numeric value upto two digit
58 | Masters | Breed Master | Breed Code should be short unique code per tenant linked to a breed name |  |  |  | Not Started | [15 empty] | No
59 | Masters | Breed Master | Breed Stage, to be fetched from (NOB/LOB) |  |  |  | Not Started | [15 empty] | No
60 | Masters | Breed Master | Breed Name, should be an alphabetical Value( LINKED WITH BREED CODE) |  |  |  | Not Started | [15 empty] | No
61 | Masters | Breed Master | Gestation Day, standard value should be measured in days (numeric value) |  |  |  | Not Started | [15 empty] | No
62 | Masters | Breed Master | Lactation Day, standard value should be kept in days (numeric value) |  |  |  | Not Started | [15 empty] | No
63 | Masters | Breed Master | Productive Life Months |  |  |  | Not Started | [15 empty] | No
64 |  | Breed Master | Residual Value Amount should be calculated or flow from BC
65 | Masters | Breed Master | Productive Lifecycle, linked with NUMBER OF PARITIES of a SOW |  |  |  | Not Started | [15 empty] | No
66 | Masters | Breed Master | Avg. Litter Size born, should be numeric value along with decimal digits . It is essential for KPI, which is to be implied at templates/scheduler |  |  |  | Not Started | [15 empty] | No
67 | Masters | Breed Master | Avg. Litter size weaned, should be a numeric value with decimal upto two digits. It is to be used in output forecast |  |  |  | Not Started | [15 empty] | No
68 | Masters | Breed Master | Avg. Weaning Weight KG (same as for AVG. LITTER SIZE) |  |  |  | Not Started | [15 empty] | No
69 | Masters | Breed Master | Farrowing Rate %, should tell about successful Farrowing post matings(AI/Natural ) in numerical values |  |  |  | Not Started | [15 empty] | No
70 | Masters | Breed Master | Boar Doses per week on every tap extraction of sperms |  |  |  | Not Started | [15 empty] | No
71 | Masters | Breed Master | Boar Productive life Months, should describe,in numerical value, specifically in months, how long a boar is productive |  |  |  | Not Started | [15 empty] | No
72 | Masters | Breed Master | Vaccination shoud be picked from vaccination shchedular |  |  |  | Not Started | [15 empty] | No
73 | Masters | Breed Master | Stage Age Labels |  |  |  | Not Started | [15 empty] | No
74 | Masters | Breed Master | Blocked (If not in use) |  |  |  | Not Started | [15 empty] | No
75 | Masters | Breeding Lifecycle Stages | Lifecycle ID, should be auto-fetched using a (breed data) {alphanumeric} |  |  |  | Not Started | [15 empty] | No
76 | Masters | Breeding Lifecycle Stages | Breed, should fetch the breed as per the lifecycle ID (alphanumeric) |  |  |  | Not Started | [15 empty] | No
77 | Masters | Breeding Lifecycle Stages | Category, should be fetched as per the animal register data |  |  |  | Not Started | [15 empty] | No
78 | Masters | Breeding Lifecycle Stages | Stage Name, should be fetched as per the animal register data |  |  |  | Not Started | [15 empty] | No
79 | Masters | Breeding Lifecycle Stages | Calculation Unit, should be fetched from period from and to.(Day/Week/Month) |  |  |  | Not Started | [15 empty] | No
80 | Masters | Breeding Lifecycle Stages | Period From, should show the start of this standard range (NUMERIC VALUE) |  |  |  | Not Started | [15 empty] | No
81 | Masters | Breeding Lifecycle Stages | Period To, shouls show the end/completionn of this standard range(NUMERIC VALUE) |  |  |  | Not Started | [15 empty] | No
82 | Masters | Breeding Lifecycle Stages | Teats Count, should be allowed upto two-digit NUMERIC VALUE
83 | Masters | Breeding Lifecycle Stages | Season Type, to be shown should contain Summer/Winter in the dropdown |  |  |  | Not Started | [15 empty] | No
84 | Masters | Breeding Lifecycle Stages | Feed Item, should be fetched as per the stage and week age of an animal(as per the ITEM MASTER) |  |  |  | Not Started | [15 empty] | No
85 | Masters | Breeding Lifecycle Stages | Feed Qty Per Head Per Day KG, should be fetched according to the scheduler |  |  |  | Not Started | [15 empty] | No
86 | Masters | Breeding Lifecycle Stages | Feed Wastage Pct, should be allowed while calculating forecast(NUMERIC VALUE) |  |  |  | Not Started | [15 empty] | No
87 | Masters | Breeding Lifecycle Stages | Std. Body Weight KG, is the expected average body weight which will be used as KPI, that is maintained on weekly basis |  |  |  | Not Started | [15 empty] | No
88 | Masters | Breeding Lifecycle Stages | Std. ADG grams per day, should show alerts, if it falls below the standard value (NUMERIC) it will be calclated as per weight gained against the feed consumed |  |  |  | Not Started | [15 empty] | No
89 | Masters | Breeding Lifecycle Stages | Std. FCR, should show alert if the FCR exceeds (NUMERIC) |  |  |  | Not Started | [15 empty] | No
90 | Masters | Breeding Lifecycle Stages | Std. Mortality Rate Pct, should allow an acceptable % of mortality at a particular stage (NUMERIC) |  |  |  | Not Started | [15 empty] | No
91 | Masters | Breeding Lifecycle Stages | Output Item, should allow expected output item at this stage for further processes (ALPHANUMERIC) |  |  |  | Not Started | [15 empty] | No
92 | Masters | Breeding Lifecycle Stages | Output UOM, should provide a dropdown of various UOMs ex-DOSE/KG/NOS |  |  |  | Not Started | [15 empty] | No
93 | Masters | Breeding Lifecycle Stages | Standard Output Qty., is the expected output per animal/sow at the end of a stage (NUMERICAL VALUE) |  |  |  | Not Started | [15 empty] | No
94 | Masters | Breeding Lifecycle Stages | Medication Protocol, should be allowed stage-wise as per SCHEDULER also |  |  |  | Not Started | [15 empty] | No
95 | Masters | Breeding Lifecycle Stages | Vaccination Protocol, should be allowed stage-wise as per SCHEDULER as well |  |  |  | Not Started | [15 empty] | No
96 | Masters | Breeding Lifecycle Stages | Resource Requirements, should be fetched according to te resource planner |  |  |  | Not Started | [15 empty] | No
97 | Masters | Breeding Lifecycle Stages | KPI lowerlimit, must provide alerts, if KPIs fall below a certain level/limit |  |  |  | Not Started | [15 empty] | No
98 | Masters | Breeding Lifecycle Stages | KPI upperlimit, must provide alerts, if the KPIs exceeds a certain level/limit |  |  |  | Not Started | [15 empty] | No
99 | Masters | Breeding Lifecycle Stages | Alert Severity, alerts should be provided as per the severity as-INFO/CRITICAL/WARNING |  |  |  | Not Started | [15 empty] | No
100 | Masters | Breeding Lifecycle Stages | Stage Notes, regarding farm instructions according to various stages should be provided at data entry screen |  |  |  | Not Started | [15 empty] | No
101 | Masters | Breeding Lifecycle Stages | Blocked, buttoon should also be provided on the page |  |  |  | Not Started | [15 empty] | No
102 | Masters | Breeding Lifecycle Stages | Created At, should be provided for the purpose of traceability (DD/MM/YYYY) |  |  |  | Not Started | [15 empty] | No
103 | Masters | Item Master | Item Code, generated from NUMBER SERIES should be unique for each item (ALPHANUMERIC) It would help even when the item type is not classified. |  |  |  | Not Started | [15 empty] | No
104 | Masters | Item Master | Item Name, should show full item name (ALPHANUMERIC) |  |  |  | Not Started | [15 empty] | No
105 | Masters | Item Master | Item Type,should be template specific, categorising item type under category and sub-category (LINKS ITEM CODE TO TYPE-CATEGORY-SUBCATEGORY) is helpful in REPORT CATEGORISATION. (mandatory) |  |  |  | Not Started | [15 empty] | No
106 | Masters | Item Master | Category of the item should show Feed / Medicine / Animal / Seeds / Chemical etc.in the dropdown for further classification of the items |  |  |  | Not Started | [15 empty] | No
107 | Masters | Item Master | Sub-Category should be provided as per the selected item category (Starter / Grower / Finisher / Layer.) ( CAN BE OR CANNOT BE) |  |  |  | Not Started | [15 empty] | No
108 | Masters | Item Master | Primary(BASE) UOM, should be shown for every transaction posted INITIALLY |  |  |  | Not Started | [15 empty] | No
109 | Masters | Item Master | Secondary UOM, should be provided as per the user's desire ( actual UOM used at a particular farm/pen) (eg-Bag) |  |  |  | Not Started | [15 empty] | No
110 | Masters | Item Master | UOM Conversion Factor, should auto-fill as per UOM Conversion Master ( Secondary UOM= break into Base UOM |  |  |  | Not Started | [15 empty] | No
111 | Masters | Item Master | Valuation Method, ( fetched from the LOB) |  |  |  | Not Started | [15 empty] | No
112 | Masters | Item Master | Standard Cost, should be allowed only if the valuation method selected is, standard (NUMERIC VALUE). Applicable on BASE UOM (CONDITIONAL) |  |  |  | Not Started | [15 empty] | No
113 | Masters | Item Master | Item Tracking, should be allowed as per LOT/SERIAL NO. if user want to or remain as NONE |  |  |  | Not Started | [15 empty] | No
114 | Masters | Item Master | Item Tracking No. Series, generated/selected as per the NUMBER SERIES of the Item TRACKING |  |  |  | Not Started | [15 empty] | No
115 | Masters | Item Master | Inventory type should be classified as INVENTORY for physical goods and NON-INVENTORY for services overhead. Items whose Stock is to be maintained are applicable for inventory. This field would have a REORDER POLICY categorised as REQUISITION ( MAX-MIN stock level) or ALERT |  |  |  | Not Started | [15 empty] | No
116 | Masters | Item Master | Min. Stock Level provided, falling below the limit must give ALERTs |  |  |  | Not Started | [15 empty] | No
117 | Masters | Item Master | Max. Stock Level, should allow maximum value of stock to be kept |  |  |  | Not Started | [15 empty] | No
118 | Masters | Item Master | Reorder Level, should enable trigger/alerts for requisition once the stock starts falling below a specific level (max-min) |  |  |  | Not Started | [15 empty] | No
119 | Masters | Item Master | Lead time days, should enable alert for the procurement of the feed every 7 days(NUMERIC) |  |  |  | Not Started | [15 empty] | No
120 | Masters | Item Master | Shelf Life Days, should enable alerts upon the expiry of a lot |  |  |  | Not Started | [15 empty] | No
121 | Masters | Item Master | Should allow Max. Storage Temperature ( Numeric Value with UOM- Degree Celsius) |  |  |  | Not Started | [15 empty] | No
122 | Masters | Item Master | Should allow Min. Storage Temperature ( Numeric Value with UOM- Degree Celsius)
123 | Masters | Item Master | Withdrawal Period Days, would specify number of days an animal would not be slaughtered (two-digit numeric value)(CONDITIONAL)
124 | Masters | Item Master | Output should be generated with a QR Code for a better traceability
125 | Masters | Item Master | Item Image URL, should allow images to view
126 | Masters | Item Master | Inventory GL Account (BC) and COGS GL ACCOUNT (BC)
127 | Masters | Item Master | By default, Item should not be blocked but there should be a BLOCK button provided for future.
128 | Masters | Item Attribute | Attribute Code, should be a short specific code generated for each item attribute (ALPHABETIC VALUE)
129 | Masters | Item Attribute | Attribute Name, should be provided accordingly
130 | Masters | Item Attribute | Data Type, should provide TEXT / NUMBER / DATE / BOOLEAN / LIST in the dropdown
131 | Masters | Item Attribute | List Values, Values for different attributes should be shown in a list format (CONDITIONAL)
132 | Masters | Item Attribute | Unit, of attributes should also be shown.(UOM master)
133 | Masters | Item Attribute | Is Mandatory
134 | Masters | Item Attribute | Affects Costing
135 | Masters | Item Attribute | Is Variant
136 | Masters | Item Attribute | Blocked, should provide a block button for user friendly access
137 | Masters | Location Master | There should be a unique Location Code per tenant generated as per number series. LOCATION TYPE should provide MAIN FARM/HOUSE/PEN with their specific codes, maintained by templates specifically made for main farm/house/pen with their sequence/series kept 1. Initially, it should be shown. A full descriptive location Address (ALPHANUMERIC with spaces ) should be allowed. SUB-LOCATION should be allowed under a MAIN LOCATION only as pre-described under the template . Further SUB-SUB LOCATION with AREA SIZE should also be allowed accordingly. AREA-UOM, should be taken from UOM MASTER. A numerical value for MAX. CAPACITY OF ANIMAL/PLANT to be placed on a particular farm should be permitted to enter. The CAPACITY UOM should be linked with UOM Master. STORAGE LOCATION should be classified as STORE/SILO. If the Storage location selected is SILO, then SILO CAPACITY KG should be allowed to enter the capacity of that particular silo. SILO REORDER DAY- when the stock left is insufficient to meet further demands, should provide ALERTS. DOWNTIME DAYS REQUIRED, should be upto two digit numeric value ( for the number of empty days at a location between two batches). The SILO should show remaining feed quantity % and a graphical representation. IMP the total of area of pens and sub locations should not excede the area of the farm location all area sizes should be specified
138 | Masters | Resource Master | RESOURCE CODE for each tenant should be unique. RESOURCE TYPE should show MANPOWER/EQUIPMENT/UTILITYin the dropdown. A full descriptive RESOURCE NAME should be allowed to write. COST PER UNIT of UOM should be NUMERIC VALUE (base currency). COST UOM should be taken/linked from/to the UOM MASTERs. Cost Element should classify as-DIRECT LABOUR/INDIRECT LABOUR/EQUIPMENT HIRE/FUEL/MAINTAINENCE. GL cost account should be applicable for resource costs and be looked up from COA. A fixed ASSET CODE should be created for EQUIPMENT only. EQUIPMENT CAPACITY should allow entering capacity of a particular ASSET only and its UOM should be looked up from UOM MASTERs. A field for EQUIPMENT SCHEDULE FIELD should be made to track Equipment Service. NEXT SERVICE DATE should be in DD/MM/YYYY format and applicable only for EQUIPMENTs. LICENCE EXPIRY date (dd/mm/yyyy) should enable ALERTS before 30 days of actual expiration of a licence.
139 | Masters | Stage Master | A short unique STAGE CODE ( CAPITAL LETTERS) for each LOB should be created, with a Number series . A desrciptive STAGE NAME should be made synced with stage codes, which should be shown at DATA ENTRY SCREEN/BATCH CARD/REPORT. Number of animals at a particular stage within a batch should also be shown.Stage CATEGORY should be categorised as PRE-PRODUCTIVE/PRODUCTIVE/OUTPUT/DISPOSAL. The TYPICAL DURATION DAYS (numeric value) should be shown in STAGE CARD. The MIN. DAYS BEFORE MOVE (numeric value) should be allowed to check pre-mature transitions of the stages. The TRANSITION TRIGGERS should be classified as AUTO-BY-DAY/MANUAL/KPI-BASED/EVENT-BASED for the stages concerned. The AUTO MOVE-ON DAY should only be created for AUTO-BY-DAY (transition trigger) for further stage. The NEXT STAGE should be auto-created upon the transition from a stage and be kept NULL if ended/completed. The ALT. NEXT STAGE should describe the stage at which the current stages goes back because of a KPI-FAILURE/EVENT fails. ALT. CONDITION should describe the condition for failure of the triggered stage. A list of KPI-CHECKS should be shown during the transition of a stage accompanied with warnings, it can be overriden by user. The stage-wise number of animals in a batch should be provided along with the access to animal register(LHS).
140 | Masters | UOM Master | A unique UOM ID should be created for each UOM. A short unique UOM CODE for each UOM should be created.The UOM name should be descriptive (alphanumerical) and shown in dropdown.
141 | Masters | UOM Conversion | ITEM should be fetched from ITEM MASTER. FROM UOM should describe the entry/purchase UOM of the desired Item. TO UOM should convert the UOM in base(primary) UOM. The CONVERSION FACTOR should show the TO UOM factors.(convert the base/primary UOM into secondary UOM)
142 | Masters | Currency Master | It must generate a specific CURRENCY CODE for each currency, with describing them (NAME OF CURRENCY) along with their SIGNs.
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152

## Dashboard
TDD Development & Testing Dashboard
KPI | Count | Priority | Count
Total Tasks | 139 | Critical | 0
Not Started | 98 | High | 0
In Progress | 0 | Medium | 0
Development Completed | 0 | Low | 0
L1 Passed | 0 | Go-Live Ready | 0
L2 Passed | 0
L3 Passed / Completed | 0
Usage: Update development and L1/L2/L3 testing statuses from the dropdowns. Overall Status, Final Testing Completion Date and Go-Live Ready are calculated automatically.

## Don't Use
Status | Development Status | Testing Status | Priority | This sheet supports dropdown lists.
Not Started | Not Started | Not Started | Critical
In Progress | In Progress | In Progress | High
On Hold | Completed | Passed | Medium
Completed | Blocked | Failed | Low
Cancelled | Rework Required | Re-test Required
| On Hold | Blocked
N/A