TRIPLE-C  ·  NAVFARM IMPLEMENTATION

Minutes of Meeting — Project Steering Committee Kick-Off

| Project | Triple-C — NAVFarm Implementation (Prudence Consulting) |
| --- | --- |
| Meeting Type | Steering Committee Kick-Off Meeting |
| Date | Tuesday, 4 August 2026; 10:00 hours Zimbabwean Time |
| Chair | Group Finance Director, Triple-C |
| Prepared By | Prudence Consulting |
| Attendees — Triple-C / Colcom | Dino Tumazos (GCEO -DT, Colcom); Ian Kennaird (CEO – Triple-C Pigs) - IK, Mandy Murebwa (Group Financial Director) - MM; Hamadzashe Mudavose (Group ICT Executive)-HM; Innocent Sithole(Group Finance Manager)-IS; John Nyabadza (Finance Manager, CCC)-JN ; Johan Odendaal (General Manager, CCC)-JO |
| Attendees — Prudence Consulting | Paul Young (Product/Project Manager) - PY; Abhinav Singh (Director)-AS; Mukul Joshi (Senior Solution Architect)-MJ; Anshu (Functional Consultant); Santos & Neha (PMO Team); Rishi & Arun (Developers) |

1.  Purpose of the Meeting

- Formal project kick-off for the NAVFarm implementation at Triple-C, covering vision, scope, roadmap, governance, risks and next steps.

- Formal introductions for Triple-C Team were introduced by DT, with IK going to be the Steercomm Chairperson going forward

- DT advised the meeting that DT, IK, MM, HM, IS, JN and JO will make up the Steercomm members from the Triple-C side with IK , being the CEO of Triple-C chairing all subsequent meetings

- PY from Prudence introduced the team for NAVFarm Implementation who will be sitting in the Steercomm, being AS, NR and PY

2.  Project Vision & Business Case – PY/AS

- Objective: digitise Triple-C's farm operations end-to-end via NAVFarm, integrated with D365 Business Central.

- Current gaps: manual feed tracking, no real-time herd valuation, scattered farm data, costly farm-level ERP access, limited profit visibility.

- NAVFarm will be the primary data-capture platform; data will flow automatically to D365BC via the NAVFarm Connector for financial valuation.

- Existing animal-health application (Pig Vision) will be integrated with NAVFarm.

3.  Solution Overview, Scope & Team - AS

- Core modules: Master Data & Farm Setup, Feed Manager, Batch & Lifecycle Management, Animal Health, Transfers, Finance/Procurement, Reporting & Dashboards (16 standard + 8 custom reports), System Integrations (RFID, Pig Vision, D365BC).

- Four years of historical data to be migrated; standard templates to be shared for data collection.

- Project team confirmed on both sides; Paul Young to act as Product/Project Manager.

- Scope is limited to items in the signed proposal — any additions to be routed through the Change Request process.

4.  Implementation Roadmap & Timeline - PY

- Phased approach: Business Process Study → Business Blueprint → System Configuration → Conference Room Pilot → Integration & Customisation → Key User Training → User Testing → Data Migration → Go-Live → Stabilisation Support.

| WBS ID | Phase / Activity | Duration (Working Days) | Mode | Start Date | End Date | Comments |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | 1. Project Kick-off | 1 | Offshore | 04-Aug-2026 | 04-Aug-2026 | Formal project launch; PMT and governance confirmed. Fixed date. |
| 2 | 2. Business Process Study | 12 | Mix-Mode | 15-Aug-2026 | 28-Aug-2026 | On-site and remote study of current farm & finance processes (7 onshore days within this window). Fixed start date, gap after kick-off for mobilisation. |
| 3 | 3. Business Blueprint | 7 | Offshore | 31-Aug-2026 | 08-Sep-2026 | Business Blueprint Document (BBP) prepared and signed off. |
| 4 | 4. System Configuration & Customization (P1) | 20 | Offshore | 09-Sep-2026 | 07-Oct-2026 | Core NAVFarm configuration per signed-off BBP. |
| 5 | 5. Conference Room Pilot (CRP) | 3 | Offshore | 08-Oct-2026 | 12-Oct-2026 | Configured solution walked through with client stakeholders. |
| 6 | 6. Integration & Customization (P2) | 20 | Offshore | 13-Oct-2026 | 12-Nov-2026 | D365BC and Pig Vision integration build. |
| 7 | 7. Key User Training | 7 | Onshore | 13-Nov-2026 | 20-Nov-2026 | May extend up to 5 additional days with joint management approval. |
| 8 | 8. User Testing | 8 | Onshore | 21-Nov-2026 | 30-Nov-2026 | May extend up to 5 additional days (combined with training) with joint management approval. |
| 9 | 9. Data Migration & Go-Live Preparation | 7 | Onshore | 01-Dec-2026 | 08-Dec-2026 | 4 years of historical data migrated (client-provided in NAVFarm template format). |
| 10 | 10. Go-Live | 5 | Onshore | 09-Dec-2026 | 14-Dec-2026 | Production cutover. |
| 11 | 11. Post Go-Live Support | 30 | Offshore | 15-Dec-2026 | 26-Jan-2027 | Stabilization support, performance tuning, issue resolution, user enablement. |
| 12 | 12. Phase 2 - System Enhancement & Integration | TBD | Offshore | TBD | TBD | Scope and timeline to be finalized separately per proposal. |

- Phase 2 (future): further process enhancements, additional MIS reports, and integrations (water meters, silo weight scales) — scope and timing to be confirmed jointly.

- AS emphasized the need to nominate project champions per site who will then be champion users/ train others. However, MM, alluded to the business experiences where training champion users always caused hurdles in implementing projects and in the past the business has resorted to training all users. MM asked HM and JN  to make some recommendations to her

- AS also indicated that they will be supplying data collection templates in preparation for detailed business process study

5.  Governance & Communication – IK/MM/AS

- Three-tier governance model: weekly Project Management Team (PMT) meetings chaired by the PMT Chairperson (MM) on Triple-C with input coming from Project Managers (PY and HM), bi-weekly Steering Committee meetings will be chaired by IK from the Triple-C with input coming from (AS) of Prudence Consulting, and Standing Committee convened as needed for escalations.

- Reporting cadence: weekly status updates, fortnightly PMO reports, regular plan-completion (RAG) reporting, and formal sign-off for change requests and milestones.

- Escalation path: Support Team → Project Manager → PMO → Project/Operations Director.

- All project documentation to be held centrally in Microsoft Teams, organised by project stage.

6.  Key Risks & Operational Considerations - PY

- Data migration accuracy — four years of historical data to be cleaned and standardised via provided templates.

- Biosecurity — hygiene protocols required for shared devices/RFID equipment near livestock; to be finalised with Triple-C.

- User adoption — reliance on shifting from paper/Excel to digital workflows; change management plan required.

- Timeline dependencies — key user availability for training/testing (up to 15 days) is a Triple-C responsibility.

7.  Resource Allocation & Change Management – IK/MM

- Triple-C to ensure timely access to data, users and infrastructure, and to nominate a farm-level champion at each site.

- Key users must be available for scheduled training and testing; contact details to be shared in advance.

- A dedicated WhatsApp/communication group to be set up for rapid issue resolution during rollout.

- Change management activities (awareness banners, early communication to end users) to begin ahead of rollout, based on prior implementation experience.

8.  Immediate Action Items / Next Steps – PY/HM

- Prudence to circulate the Master Data template (Excel) and project governance/PMT documents.

- Triple-C to confirm project team credentials, contact numbers and email IDs for all stakeholders.

- Prudence to share the detailed project plan / Gantt chart, including a company holiday calendar input from Triple-C.

- Triple-C to share the holiday calendar with us

Meeting ended at 11:30 Hours - Next Steering Committee meeting: to be confirmed.