TRIPLE-C  ·  NAVFARM IMPLEMENTATION

Minutes of Meeting — Project Plan Walkthrough & Kickoff Recap

| Project | Triple-C — NAVFarm Implementation (Prudence Consulting) |
| --- | --- |
| Meeting Type | Project Management Team (PMT) Meeting — Project Plan Walkthrough & Kick-off Recap |
| Date | Follow-up session, week commencing 4 August 2026 – 11:30 |
| Mode | Hybrid — select stakeholders joined digitally |
| Attendees — Triple-C PMT | Full roster as confirmed at kick-off (Section 2 below); Mercantile Bank representative also joined digitally for finance/banking-integration input |
| Attendees — Prudence Consulting | Paul Young (PY) (Product/Project Manager); Abhinav Singh (AS) (Director); Mukul Joshi (MJ) (Senior Solution Architect); Anshu (Functional Consultant); Santos & Neha (PMO Team); Rishi & Arun (Developers) |

1.  Purpose of the Meeting

- Project Management Team (PMT) working session — to map out implementation activities in order to answer to business needs as set out by Project Steering Committee. The session covered Project plan and the methodology that will be used for implementation of NAVFARM solution – PY and AS appraised the PMTwith a detailed project plan (timeline, milestones and WBS).

2.  Attendees — Full PMT Roaster

- Full Triple-C PMT membership, as confirmed and shared at kick-off, listed below for reference.

Triple-C

| # | Name | Title | Project Role |
| --- | --- | --- | --- |
| 1 | Mandy Murebwa (MM) | Group Finance Director | Project Management Chairperson |
| 2 | Hama Mudavose (HM) | Group ICT Executive | Project Management Role |
| 3 | Johan Odendaal (JO) | General Manager | Farm Operations Implementation Lead |
| 4 | Innocent Sithole (IS) | Group Financial Manager | Financial Controls |
| 5 | John Nyabadza (JN) | Finance Manager | Finance Lead Role - Triple-C |
| 6 | Israel Muchuchu (IM) | Human Resources Manager | Human Capital Resource Management |
| 7 | Lara Baum (LM) | Farm Manager - Multiplier | Farm Operations (Multiplier) |
| 8 | Ngoni Dedza (ND) | Mill Manager | Milling Operations - Transfer Orders |
| 9 | Jimmyson Kazangarare (JK) | Farm Manager - Porta | Farm Operations (Porta) |
| 10 | Solomon Maposa (SM) | Farm Manager - Richlands | Farm Operations (Richlands) |
| 11 | Archbald Gwebere (AG) | Data Analyst | Data Analyst - Farming Operations |
| 12 | Tafadzwa Katsokore (TK) | Farm Supervisor | Lions Head Farm Operations |
| 13 | Willis Mudzonga (WM) | Farm Supervisor | Villa Franca Farm Operations |
| 14 | Trevor Mudimu ™ | Farm Supervisor | Learig Farm Operations |
| 15 | Runyararo Sithole (RS) | ICT Systems Administrator | ICT Technical Implementation - Triple-C |
| 16 | David Zvinoitavamwe (DZ) | ICT Manager | ICT Technical Implementation |
| 17 | Tonderai Gonamombe (tG) | Management Accountant | Costing Role |
| 18 | Fungai Sigauke (FS) | Site Manager - Learig | Farm Operations (Learig) |
| 19 | Gerd Baum (GM) | Farm Manager - Grasmere | Farm Operations (Grasmere) |
| 20 | Johan Fourie (JF) | Farm Manager - LionHead | Farm Operations (LionHead) |
| 21 | Tapiwa Mupambuzi ™ | Farm Manager - Villa Franca | Farm Operations (Villa Franca) |

3.  Recap of Kick-Off Presentation – PY/AS

- Kick-off deck (PPT) was presented as a refresher, covering: project vision & business case, solution overview, scope & team, governance model, and operational/risk considerations.

- Purpose was to bring PMT team who missed context up to speed on decisions and direction agreed at the Steering Committee Kick-Off.

4.  Project Plan Walkthrough — Timeline & Milestones - PY

Key Milestones Presented

| No. | Milestone | Target Date |
| --- | --- | --- |
| M1 | Project Kick-off Complete | 04 Aug 2026 |
| M2 | Business Blueprint Sign-off | 08 Sep 2026 |
| M3 | Conference Room Pilot (CRP) Sign-off | 12 Oct 2026 |
| M4 | Integration & Customization Complete | 12 Nov 2026 |
| M5 | Key User Training Complete | 20 Nov 2026 |
| M6 | User Testing (UAT) Complete | 30 Nov 2026 |
| M7 | Data Migration Complete | 08 Dec 2026 |
| M8 | Go-Live | 14 Dec 2026 |
| M9 | Project Closure | 26 Jan 2027 |

5.  Work Breakdown Structure (WBS) — Tasks & Sub-Tasks - PY

- Plan is structured hierarchically: Phase → Work Package → Deliverable/Task, each mapped to a WBS ID, owner, mode (onshore/offshore/joint) and timeline.

- Example: Phase 4 (System Configuration) breaks into work packages such as Master Data & Farm Setup, Feed Management, Batch & Lifecycle Management, Animal Health, RFID Capabilities, Applications & Field Capture, and Finance & Procurement — each with individually tracked deliverables.

- Ownership is clearly split: Prudence-led configuration/development tasks vs. jointly-owned tasks (e.g. UAT, data migration, go-live readiness) requiring Triple-C participation.

- This structure gives both teams visibility of what outcome is due, by whom, and by which date, at a task and sub-task level — not just at the phase level.

Detailed WBS & Schedule - PY

| WBS ID | Phase / Activity | Duration (Working Days) | Mode | Start Date | End Date | Comments |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | 1. Project Kick-off | 1 | Offshore | 04-Aug-2026 | 04-Aug-2026 | Formal project launch; PMT and governance confirmed. Fixed date. |
| 2 | 2. Business Process Study | 12 | Mix-Mode | 15-Aug-2026 | 28-Aug-2026 | On-site and remote study of current farm & finance processes (7 onshore days within this window). Fixed start date, gap after kick-off for mobilisation. |
| 3 | 3. Business Blueprint | 7 | Offshore | 31-Aug-2026 | 08-Sep-2026 | Business Blueprint Document (BBP) prepared and signed off. |
| 4 | 4. System Configuration & Customization (P1) | 20 | Offshore | 09-Sep-2026 | 07-Oct-2026 | Core NAVFarm configuration per signed-off BBP. |
| 5 | 5. Conference Room Pilot (CRP) | 3 | Offshore | 08-Oct-2026 | 12-Oct-2026 | Configured solution walked through with client stakeholders. |
| 6 | 6. Integration & Customization (P2) | 20 | Offshore | 13-Oct-2026 | 12-Nov-2026 | D365BC and Pig Vision integration build. |
| 7 | 7. Key User Training | 7 | Onshore | 13-Nov-2026 | 20-Nov-2026 | May extend up to 5 additional days with joint management approval. |
| 8 | 8. User Testing | 8 | Onshore | 21-Nov-2026 | 30-Nov-2026 | May extend up to 5 additional days (combined with training) with joint management approval. |
| 9 | 9. Data Migration & Go-Live Preparation | 7 | Onshore | 01-Dec-2026 | 08-Dec-2026 | 4 years of historical data migrated (client-provided in NAVFarm template format). |
| 10 | 10. Go-Live | 5 | Onshore | 09-Dec-2026 | 14-Dec-2026 | Production cutover. |
| 11 | 11. Post Go-Live Support | 30 | Offshore | 15-Dec-2026 | 26-Jan-2027 | Stabilization support, performance tuning, issue resolution, user enablement. |
| 12 | 12. Phase 2 - System Enhancement & Integration | TBD | Offshore | TBD | TBD | Scope and timeline to be finalized separately per proposal. |

6.  Q&A — Dashboards & Access Roles - PY

- Question raised: who can see what on the dashboards, and whether access will be role-based.

- Query raised: whether individual/personalised dashboards will be available, or only shared views.

- Clarified and confirmed: NAVFarm supports role-based access control, with different dashboards and permissions configurable by user role (e.g. supervisor-level vs. stakeholder-level views).

- Detailed access-role mapping (who sees which farm/module/report) to be finalised jointly

7.  Specialist Input - PY

- JN and JO joined to provide specialist input on their respective areas of expertise.

- Additional points and clarifications were raised by other attendees during the session and noted for follow-up where applicable.

8.  Action Items / Next Steps - PY

- Prudence to circulate the project plan (Timeline, Milestones, WBS) and kick-off deck to all stakeholders for reference.

- Triple-C to review the WBS ownership split and flag any resourcing concerns ahead of the Business Process Study.

- Prudence to finalise the role-based access and dashboard permission matrix jointly with Triple-C on a later stage.

- Triple-C to confirm its holiday/closure list so the plan's working-day calendar can be finalised.

- Prudence will create a shared folder for communication and as a repository of project documents

Next session: to be confirmed.