## Timeline
Project Timeline - Phase Level (Working Days)
WBS ID | Phase / Activity | Duration (Working Days) | Mode | Fixed Start (optional) | Start Date | End Date | Comments
1 | 1. Project Kick-off | 1 | Offshore | 2026-08-04 | 2026-08-04 | 2026-08-04 | Formal project launch; PMT and governance confirmed. Fixed date.
2 | 2. Business Process Study | 12 | Mix-Mode | 2026-08-15 | 2026-08-15 | 2026-08-28 | On-site and remote study of current farm & finance processes (7 onshore days within this window). Fixed start date, gap after kick-off for mobilisation.
3 | 3. Business Blueprint | 7 | Offshore |  | 2026-08-31 | 2026-09-08 | Business Blueprint Document (BBP) prepared and signed off.
4 | 4. System Configuration & Customization (P1) | 20 | Offshore |  | 2026-09-09 | 2026-10-07 | Core NAVFarm configuration per signed-off BBP.
5 | 5. Conference Room Pilot (CRP) | 3 | Offshore |  | 2026-10-08 | 2026-10-12 | Configured solution walked through with client stakeholders.
6 | 6. Integration & Customization (P2) | 20 | Offshore |  | 2026-10-13 | 2026-11-12 | D365BC and Pig Vision integration build.
7 | 7. Key User Training | 7 | Onshore |  | 2026-11-13 | 2026-11-20 | May extend up to 5 additional days with joint management approval.
8 | 8. User Testing | 8 | Onshore |  | 2026-11-21 | 2026-11-30 | May extend up to 5 additional days (combined with training) with joint management approval.
9 | 9. Data Migration & Go-Live Preparation | 7 | Onshore |  | 2026-12-01 | 2026-12-08 | 4 years of historical data migrated (client-provided in NAVFarm template format).
10 | 10. Go-Live | 5 | Onshore |  | 2026-12-09 | 2026-12-14 | Production cutover.
11 | 11. Post Go-Live Support | 30 | Offshore |  | 2026-12-15 | 2027-01-26 | Stabilization support, performance tuning, issue resolution, user enablement.
12 | 12. Phase 2 - System Enhancement & Integration | TBD | Offshore |  | TBD | TBD | Scope and timeline to be finalized separately per proposal.
| Total Phase 1 Duration (Working Days) | 120
| Go-Live Date | 2026-12-14
| Project Closure (Post Go-Live Support End) | 2027-01-26
| Total Calendar Span (Kick-off to Closure, days) | 176

## Milestones
Project Milestones
No. | Milestone | Target Date | Description / Exit Criteria
M1 | Project Kick-off Complete | 2026-08-04 | Project charter confirmed, PMT, governance model and communication plan agreed.
M2 | Business Blueprint Sign-off | 2026-09-08 | Business Blueprint Document reviewed and signed off by both parties.
M3 | Conference Room Pilot (CRP) Sign-off | 2026-10-12 | Configured solution demonstrated and accepted by client stakeholders.
M4 | Integration & Customization Complete | 2026-11-12 | NAVFarm-D365BC and NAVFarm-Pig Vision integrations built and unit tested.
M5 | Key User Training Complete | 2026-11-20 | Key users trained at the centralized location (Head Office).
M6 | User Testing (UAT) Complete | 2026-11-30 | User acceptance testing completed and signed off.
M7 | Data Migration Complete | 2026-12-08 | 4 years of historical pig farm data migrated and validated in NAVFarm.
M8 | Go-Live | 2026-12-14 | Production cutover, NAVFarm live across all farms.
M9 | Project Closure (Post Go-Live Support End) | 2027-01-26 | 1-month stabilization support complete, project handed to AMC/support agreement.

## Detailed WBS
Detailed Work Breakdown Structure - Phase 1
WBS ID | Phase / Activity | Work Package | Deliverable / Task | Start Date | End Date | Mode | Owner
1.1.1 | 1. Project Kick-off | Project Launch | Project charter and governance model confirmed | 2026-08-04 | 2026-08-04 | Offshore | Joint (Client & Prudence)
1.1.2 | 1. Project Kick-off | Project Launch | Project Management Team (PMT) introduced and roles agreed | 2026-08-04 | 2026-08-04 | Offshore | Joint (Client & Prudence)
1.1.3 | 1. Project Kick-off | Project Launch | Communication plan and meeting cadence agreed | 2026-08-04 | 2026-08-04 | Offshore | Joint (Client & Prudence)
2.1.1 | 2. Business Process Study | Farm Process Walkthroughs | Feed, health, breeding and mortality workflows reviewed, farm by farm | 2026-08-15 | 2026-08-28 | Mix-Mode | Joint (Client & Prudence)
2.1.2 | 2. Business Process Study | Farm Process Walkthroughs | Current reporting structure and MIS reviewed | 2026-08-15 | 2026-08-28 | Mix-Mode | Joint (Client & Prudence)
2.1.3 | 2. Business Process Study | Farm Process Walkthroughs | Roles and responsibilities of farm and finance staff reviewed | 2026-08-15 | 2026-08-28 | Mix-Mode | Joint (Client & Prudence)
2.2.1 | 2. Business Process Study | Documentation | Current-state process documentation | 2026-08-15 | 2026-08-28 | Mix-Mode | Prudence Consulting
2.2.2 | 2. Business Process Study | Documentation | Gap analysis against NAVFarm standard functionality | 2026-08-15 | 2026-08-28 | Mix-Mode | Prudence Consulting
3.1.1 | 3. Business Blueprint | Business Blueprint | Business Blueprint Document (BBP) prepared | 2026-08-31 | 2026-09-08 | Offshore | Joint (Client & Prudence)
3.1.2 | 3. Business Blueprint | Business Blueprint | Blueprint review workshops with Triple-C stakeholders | 2026-08-31 | 2026-09-08 | Offshore | Joint (Client & Prudence)
3.1.3 | 3. Business Blueprint | Business Blueprint | Blueprint sign-off by both parties | 2026-08-31 | 2026-09-08 | Offshore | Joint (Client & Prudence)
4.1.1 | 4. System Configuration & Customization (P1) | Master Data & Farm Setup | Breed Master | 2026-09-09 | 2026-10-07 | Offshore | Prudence Consulting
4.1.2 | 4. System Configuration & Customization (P1) | Master Data & Farm Setup | Animal Register | 2026-09-09 | 2026-10-07 | Offshore | Prudence Consulting
4.1.3 | 4. System Configuration & Customization (P1) | Master Data & Farm Setup | Location, Sub-Location & Sub-Sub-Location hierarchy | 2026-09-09 | 2026-10-07 | Offshore | Prudence Consulting
4.1.4 | 4. System Configuration & Customization (P1) | Master Data & Farm Setup | Farm Store / Silo Allocation | 2026-09-09 | 2026-10-07 | Offshore | Prudence Consulting
4.1.5 | 4. System Configuration & Customization (P1) | Master Data & Farm Setup | Item Master and Attributes | 2026-09-09 | 2026-10-07 | Offshore | Prudence Consulting
4.1.6 | 4. System Configuration & Customization (P1) | Master Data & Farm Setup | Farm Resource Creation | 2026-09-09 | 2026-10-07 | Offshore | Prudence Consulting
4.2.1 | 4. System Configuration & Customization (P1) | Feed Management | Feed Forecast Planning (demand driven by population, growth stage & inventory) | 2026-09-09 | 2026-10-07 | Offshore | Prudence Consulting
4.2.2 | 4. System Configuration & Customization (P1) | Feed Management | Feed Forecast Report | 2026-09-09 | 2026-10-07 | Offshore | Prudence Consulting
4.2.3 | 4. System Configuration & Customization (P1) | Feed Management | Automated feed cost posting | 2026-09-09 | 2026-10-07 | Offshore | Prudence Consulting
4.3.1 | 4. System Configuration & Customization (P1) | Batch & Lifecycle Management | Batch Scheduler | 2026-09-09 | 2026-10-07 | Offshore | Prudence Consulting
4.3.2 | 4. System Configuration & Customization (P1) | Batch & Lifecycle Management | Batch Creation | 2026-09-09 | 2026-10-07 | Offshore | Prudence Consulting
4.3.3 | 4. System Configuration & Customization (P1) | Batch & Lifecycle Management | Resource Allocation to Batch | 2026-09-09 | 2026-10-07 | Offshore | Prudence Consulting
4.3.4 | 4. System Configuration & Customization (P1) | Batch & Lifecycle Management | Stage-wise Data Entry | 2026-09-09 | 2026-10-07 | Offshore | Prudence Consulting
4.3.5 | 4. System Configuration & Customization (P1) | Batch & Lifecycle Management | Animal Transfer Traceability | 2026-09-09 | 2026-10-07 | Offshore | Prudence Consulting
4.3.6 | 4. System Configuration & Customization (P1) | Batch & Lifecycle Management | End-to-end Pig Lifecycle Tracking (birth to market) | 2026-09-09 | 2026-10-07 | Offshore | Prudence Consulting
4.4.1 | 4. System Configuration & Customization (P1) | Animal Health | Animal Health Card & History | 2026-09-09 | 2026-10-07 | Offshore | Prudence Consulting
4.5.1 | 4. System Configuration & Customization (P1) | Transfers | Transfer Request | 2026-09-09 | 2026-10-07 | Offshore | Prudence Consulting
4.5.2 | 4. System Configuration & Customization (P1) | Transfers | Transfer In / Out | 2026-09-09 | 2026-10-07 | Offshore | Prudence Consulting
4.6.1 | 4. System Configuration & Customization (P1) | RFID & AI-Enabled Capabilities | RFID Integration with NAVFarm App | 2026-09-09 | 2026-10-07 | Offshore | Prudence Consulting
4.6.2 | 4. System Configuration & Customization (P1) | RFID & AI-Enabled Capabilities | AI-Schedule | 2026-09-09 | 2026-10-07 | Offshore | Prudence Consulting
4.6.3 | 4. System Configuration & Customization (P1) | RFID & AI-Enabled Capabilities | AI-Parameters | 2026-09-09 | 2026-10-07 | Offshore | Prudence Consulting
4.6.4 | 4. System Configuration & Customization (P1) | RFID & AI-Enabled Capabilities | AI-Semen Production | 2026-09-09 | 2026-10-07 | Offshore | Prudence Consulting
4.6.5 | 4. System Configuration & Customization (P1) | RFID & AI-Enabled Capabilities | QR Code Generation & Traceability (Semen) | 2026-09-09 | 2026-10-07 | Offshore | Prudence Consulting
4.6.6 | 4. System Configuration & Customization (P1) | RFID & AI-Enabled Capabilities | Lot Tracking - AI (Expiry Calculation) | 2026-09-09 | 2026-10-07 | Offshore | Prudence Consulting
4.6.7 | 4. System Configuration & Customization (P1) | RFID & AI-Enabled Capabilities | AI-Cost Allocation | 2026-09-09 | 2026-10-07 | Offshore | Prudence Consulting
4.7.1 | 4. System Configuration & Customization (P1) | Applications & Field Capture | Web Application | 2026-09-09 | 2026-10-07 | Offshore | Prudence Consulting
4.7.2 | 4. System Configuration & Customization (P1) | Applications & Field Capture | Mobile App (Online / Offline) | 2026-09-09 | 2026-10-07 | Offshore | Prudence Consulting
4.7.3 | 4. System Configuration & Customization (P1) | Applications & Field Capture | Picture Saving (stage-wise / data-entry-wise) | 2026-09-09 | 2026-10-07 | Offshore | Prudence Consulting
4.8.1 | 4. System Configuration & Customization (P1) | Finance & Procurement Functions | Procurement Requisitions Function in NAVFarm | 2026-09-09 | 2026-10-07 | Offshore | Prudence Consulting
4.8.2 | 4. System Configuration & Customization (P1) | Finance & Procurement Functions | Petty Cash Requisitions Function in NAVFarm | 2026-09-09 | 2026-10-07 | Offshore | Prudence Consulting
5.1.1 | 5. Conference Room Pilot (CRP) | Dashboards & Reporting | Real-time performance dashboards | 2026-10-08 | 2026-10-12 | Offshore | Prudence Consulting
5.1.2 | 5. Conference Room Pilot (CRP) | Dashboards & Reporting | 16 standard reports (Animal Medical, Feed Consumption, Stock, Traceability, Cost, etc.) | 2026-10-08 | 2026-10-12 | Offshore | Prudence Consulting
5.1.3 | 5. Conference Room Pilot (CRP) | Dashboards & Reporting | 8 custom reports (finalized during Business Process Study) | 2026-10-08 | 2026-10-12 | Offshore | Prudence Consulting
6.1.1 | 6. Integration & Customization (P2) | System Integration | NAVFarm Connector (real-time API layer, data transfer & log management) | 2026-10-13 | 2026-11-12 | Offshore | Prudence Consulting
6.1.2 | 6. Integration & Customization (P2) | System Integration | NAVFarm to D365BC Integration for Stock Transfer | 2026-10-13 | 2026-11-12 | Offshore | Prudence Consulting
6.1.3 | 6. Integration & Customization (P2) | System Integration | Bio-Logical Module - Amortization Engine @ D365BC | 2026-10-13 | 2026-11-12 | Offshore | Prudence Consulting
6.1.4 | 6. Integration & Customization (P2) | System Integration | Batch-wise & Stage-wise Traceability (Farm to Fork) | 2026-10-13 | 2026-11-12 | Offshore | Prudence Consulting
6.1.5 | 6. Integration & Customization (P2) | System Integration | NAVFarm - Pig Vision Integration (bi-directional data exchange via APIs) | 2026-10-13 | 2026-11-12 | Offshore | Prudence Consulting
7.1.1 | 7. Key User Training | Key User Training | Training material and user guides prepared | 2026-11-13 | 2026-11-20 | Onshore | Prudence Consulting
7.1.2 | 7. Key User Training | Key User Training | Key user training sessions delivered at Head Office | 2026-11-13 | 2026-11-20 | Onshore | Prudence Consulting
7.1.3 | 7. Key User Training | Key User Training | Training attendance and sign-off | 2026-11-13 | 2026-11-20 | Onshore | Prudence Consulting
8.1.1 | 8. User Testing | User Acceptance Testing (UAT) | UAT test scenarios and scripts prepared | 2026-11-21 | 2026-11-30 | Onshore | Joint (Client & Prudence)
8.1.2 | 8. User Testing | User Acceptance Testing (UAT) | UAT executed by key users against real farm scenarios | 2026-11-21 | 2026-11-30 | Onshore | Joint (Client & Prudence)
8.1.3 | 8. User Testing | User Acceptance Testing (UAT) | Defects logged, triaged and resolved | 2026-11-21 | 2026-11-30 | Onshore | Joint (Client & Prudence)
8.1.4 | 8. User Testing | User Acceptance Testing (UAT) | UAT sign-off by Triple-C | 2026-11-21 | 2026-11-30 | Onshore | Joint (Client & Prudence)
9.1.1 | 9. Data Migration & Go-Live Preparation | Data Migration | 4 years of historical pig farm data prepared in NAVFarm template format (client) | 2026-12-01 | 2026-12-08 | Onshore | Joint (Client & Prudence)
9.1.2 | 9. Data Migration & Go-Live Preparation | Data Migration | Data validation and load into NAVFarm (Prudence, with client assistance) | 2026-12-01 | 2026-12-08 | Onshore | Joint (Client & Prudence)
9.1.3 | 9. Data Migration & Go-Live Preparation | Data Migration | Go-Live readiness checklist sign-off | 2026-12-01 | 2026-12-08 | Onshore | Joint (Client & Prudence)
10.1.1 | 10. Go-Live | Go-Live | Go-Live readiness checklist confirmed | 2026-12-09 | 2026-12-14 | Onshore | Joint (Client & Prudence)
10.1.2 | 10. Go-Live | Go-Live | Production cutover across all farms | 2026-12-09 | 2026-12-14 | Onshore | Joint (Client & Prudence)
10.1.3 | 10. Go-Live | Go-Live | Hypercare support begins | 2026-12-09 | 2026-12-14 | Onshore | Joint (Client & Prudence)
11.1.1 | 11. Post Go-Live Support | Post Go-Live Stabilization | Stabilization support | 2026-12-15 | 2027-01-26 | Offshore | Prudence Consulting
11.1.2 | 11. Post Go-Live Support | Post Go-Live Stabilization | Performance tuning | 2026-12-15 | 2027-01-26 | Offshore | Prudence Consulting
11.1.3 | 11. Post Go-Live Support | Post Go-Live Stabilization | Issue resolution | 2026-12-15 | 2027-01-26 | Offshore | Prudence Consulting
11.1.4 | 11. Post Go-Live Support | Post Go-Live Stabilization | User enablement | 2026-12-15 | 2027-01-26 | Offshore | Prudence Consulting
P2 | Phase 2 - System Enhancement & Integration (scope & timeline TBD)
P2.1 | 12. Phase 2 - System Enhancement & Integration | Process Enhancement | Process enhancement on the NAVFarm platform | TBD | TBD | Offshore | Prudence Consulting
P2.2 | 12. Phase 2 - System Enhancement & Integration | Reporting | New report / MIS development on NAVFarm or D365BC | TBD | TBD | Offshore | Prudence Consulting
P2.3 | 12. Phase 2 - System Enhancement & Integration | IoT Integration | NAVFarm integration with water meters | TBD | TBD | Offshore | Prudence Consulting
P2.4 | 12. Phase 2 - System Enhancement & Integration | IoT Integration | NAVFarm integration with silo weight scales | TBD | TBD | Offshore | Prudence Consulting
P2.5 | 12. Phase 2 - System Enhancement & Integration | IoT Integration | Any other device/equipment integrations, as required | TBD | TBD | Offshore | Prudence Consulting
Formulas:
Start Date = INDEX(Timeline!$F3:F13,MATCH([Phase / Activity],Timeline!$B3:B13,0))
End Date = INDEX(Timeline!$G3:G13,MATCH([Phase / Activity],Timeline!$B3:B13,0))

## holidays
Holidays / Non-Working Days - Customer (Triple-C)
Date | Holiday / Closure Name
2026-08-11 | EXAMPLE - Heroes Day (replace with your confirmed holiday list)

## Prudence Holidays
Holidays / Non-Working Days- Prudence Consulting
Date | Holiday / Closure Name
2026-08-28 | Raksha Bandhan
2026-10-02 | Mahatma Gandhi Jayanti
2026-10-20 | Dussehra
2026-11-09 | Govardhan Puja
2026-11-11 | Bhai Dooj
2026-11-24 | Gurpurab
2026-12-25 | Christmas

## About wbs
Triple-C - NAVFARM Implementation
Project Plan: Working-Day Timeline, Milestones & Detailed WBS
Two working calendars are used, based on each activity's Mode
- Mode = Mix-Mode or Onshore -> follows the CUSTOMER (Triple-C) calendar: Monday to Saturday, Sunday off, plus any date on the 'holidays' sheet.
- Mode = Offshore -> follows the PRUDENCE calendar: Monday to Friday only (Saturday and Sunday off), plus any date on the 'Prudence Holidays' sheet.
- Every date on the Timeline, Milestones and Detailed WBS sheets is calculated automatically using whichever calendar applies to that activity's Mode.
- Add or change a holiday on either holiday sheet and the whole plan recalculates and shifts automatically.
Fixed (anchor) dates
- Project Kick-off is fixed to 04-Aug-2026 (Timeline sheet, cell E7).
- Business Process Study is fixed to start 15-Aug-2026 (Timeline sheet, cell E8) - there is a deliberate gap after kick-off for mobilisation.
- Every other activity is chained automatically: it starts on the next working day (per its own Mode's calendar) after the previous activity ends.
- To fix any other activity to a specific start date, type that date into its 'Fixed Start' cell (column E) on the Timeline sheet. Leave it blank to let the plan auto-chain.
How to use this workbook
1. Add Triple-C public holidays / closure days to the 'holidays' sheet.
2. Add Prudence Consulting holidays to the 'Prudence Holidays' sheet.
3. Timeline (Phase-Level): all 11 Phase 1 activities, with working-day durations, Mode, start and end dates.
4. Milestones: 9 key sign-off / completion dates, linked live to the Timeline sheet.
5. Detailed WBS: deliverable-level breakdown, grouped under each Phase 1 activity; dates pulled automatically from the Timeline sheet.
6. Calendar_Dont Use this: the underlying working-day calendar for both calendars. You shouldn't need to edit this sheet directly.
Source
Durations, phases and deliverables are taken from the Prudence Consulting Business Proposal (Enterprise Pig Farming Transformation Proposal, v0.4). Working-day durations use the same day-counts as the proposal's implementation plan.

## Calendar_Dont Use this
Working-Day Calendar (helper sheet - drives all date calculations)
We shouldn't need to edit this sheet.
Date | Day | Is Saturday? | Is Sunday? | Is Customer Holiday? | Is Prudence Holiday? | Working Day - Customer (Mon-Sat) | Working Day - Prudence (Mon-Fri) | Cumulative Working Days - Customer | Cumulative Working Days - Prudence
2026-07-15 | Wed | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1
2026-07-16 | Thu | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 2
2026-07-17 | Fri | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 3
2026-07-18 | Sat | 1 | 0 | 0 | 0 | 1 | 0 | 4 | 3
2026-07-19 | Sun | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 3
2026-07-20 | Mon | 0 | 0 | 0 | 0 | 1 | 1 | 5 | 4
2026-07-21 | Tue | 0 | 0 | 0 | 0 | 1 | 1 | 6 | 5
2026-07-22 | Wed | 0 | 0 | 0 | 0 | 1 | 1 | 7 | 6
2026-07-23 | Thu | 0 | 0 | 0 | 0 | 1 | 1 | 8 | 7
2026-07-24 | Fri | 0 | 0 | 0 | 0 | 1 | 1 | 9 | 8
2026-07-25 | Sat | 1 | 0 | 0 | 0 | 1 | 0 | 10 | 8
2026-07-26 | Sun | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 8
2026-07-27 | Mon | 0 | 0 | 0 | 0 | 1 | 1 | 11 | 9
2026-07-28 | Tue | 0 | 0 | 0 | 0 | 1 | 1 | 12 | 10
2026-07-29 | Wed | 0 | 0 | 0 | 0 | 1 | 1 | 13 | 11
2026-07-30 | Thu | 0 | 0 | 0 | 0 | 1 | 1 | 14 | 12
2026-07-31 | Fri | 0 | 0 | 0 | 0 | 1 | 1 | 15 | 13
2026-08-01 | Sat | 1 | 0 | 0 | 0 | 1 | 0 | 16 | 13
2026-08-02 | Sun | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 13
2026-08-03 | Mon | 0 | 0 | 0 | 0 | 1 | 1 | 17 | 14
2026-08-04 | Tue | 0 | 0 | 0 | 0 | 1 | 1 | 18 | 15
2026-08-05 | Wed | 0 | 0 | 0 | 0 | 1 | 1 | 19 | 16
2026-08-06 | Thu | 0 | 0 | 0 | 0 | 1 | 1 | 20 | 17
2026-08-07 | Fri | 0 | 0 | 0 | 0 | 1 | 1 | 21 | 18
2026-08-08 | Sat | 1 | 0 | 0 | 0 | 1 | 0 | 22 | 18
2026-08-09 | Sun | 0 | 1 | 0 | 0 | 0 | 0 | 22 | 18
2026-08-10 | Mon | 0 | 0 | 0 | 0 | 1 | 1 | 23 | 19
2026-08-11 | Tue | 0 | 0 | 1 | 0 | 0 | 1 | 23 | 20
2026-08-12 | Wed | 0 | 0 | 0 | 0 | 1 | 1 | 24 | 21
2026-08-13 | Thu | 0 | 0 | 0 | 0 | 1 | 1 | 25 | 22
2026-08-14 | Fri | 0 | 0 | 0 | 0 | 1 | 1 | 26 | 23
2026-08-15 | Sat | 1 | 0 | 0 | 0 | 1 | 0 | 27 | 23
2026-08-16 | Sun | 0 | 1 | 0 | 0 | 0 | 0 | 27 | 23
2026-08-17 | Mon | 0 | 0 | 0 | 0 | 1 | 1 | 28 | 24
2026-08-18 | Tue | 0 | 0 | 0 | 0 | 1 | 1 | 29 | 25
2026-08-19 | Wed | 0 | 0 | 0 | 0 | 1 | 1 | 30 | 26
2026-08-20 | Thu | 0 | 0 | 0 | 0 | 1 | 1 | 31 | 27
2026-08-21 | Fri | 0 | 0 | 0 | 0 | 1 | 1 | 32 | 28
2026-08-22 | Sat | 1 | 0 | 0 | 0 | 1 | 0 | 33 | 28
2026-08-23 | Sun | 0 | 1 | 0 | 0 | 0 | 0 | 33 | 28
2026-08-24 | Mon | 0 | 0 | 0 | 0 | 1 | 1 | 34 | 29
2026-08-25 | Tue | 0 | 0 | 0 | 0 | 1 | 1 | 35 | 30
2026-08-26 | Wed | 0 | 0 | 0 | 0 | 1 | 1 | 36 | 31
2026-08-27 | Thu | 0 | 0 | 0 | 0 | 1 | 1 | 37 | 32
2026-08-28 | Fri | 0 | 0 | 0 | 1 | 1 | 0 | 38 | 32
2026-08-29 | Sat | 1 | 0 | 0 | 0 | 1 | 0 | 39 | 32
2026-08-30 | Sun | 0 | 1 | 0 | 0 | 0 | 0 | 39 | 32
2026-08-31 | Mon | 0 | 0 | 0 | 0 | 1 | 1 | 40 | 33
2026-09-01 | Tue | 0 | 0 | 0 | 0 | 1 | 1 | 41 | 34
2026-09-02 | Wed | 0 | 0 | 0 | 0 | 1 | 1 | 42 | 35
2026-09-03 | Thu | 0 | 0 | 0 | 0 | 1 | 1 | 43 | 36
2026-09-04 | Fri | 0 | 0 | 0 | 0 | 1 | 1 | 44 | 37
2026-09-05 | Sat | 1 | 0 | 0 | 0 | 1 | 0 | 45 | 37
2026-09-06 | Sun | 0 | 1 | 0 | 0 | 0 | 0 | 45 | 37
2026-09-07 | Mon | 0 | 0 | 0 | 0 | 1 | 1 | 46 | 38
2026-09-08 | Tue | 0 | 0 | 0 | 0 | 1 | 1 | 47 | 39
2026-09-09 | Wed | 0 | 0 | 0 | 0 | 1 | 1 | 48 | 40
2026-09-10 | Thu | 0 | 0 | 0 | 0 | 1 | 1 | 49 | 41
2026-09-11 | Fri | 0 | 0 | 0 | 0 | 1 | 1 | 50 | 42
2026-09-12 | Sat | 1 | 0 | 0 | 0 | 1 | 0 | 51 | 42
2026-09-13 | Sun | 0 | 1 | 0 | 0 | 0 | 0 | 51 | 42
2026-09-14 | Mon | 0 | 0 | 0 | 0 | 1 | 1 | 52 | 43
2026-09-15 | Tue | 0 | 0 | 0 | 0 | 1 | 1 | 53 | 44
2026-09-16 | Wed | 0 | 0 | 0 | 0 | 1 | 1 | 54 | 45
2026-09-17 | Thu | 0 | 0 | 0 | 0 | 1 | 1 | 55 | 46
2026-09-18 | Fri | 0 | 0 | 0 | 0 | 1 | 1 | 56 | 47
2026-09-19 | Sat | 1 | 0 | 0 | 0 | 1 | 0 | 57 | 47
2026-09-20 | Sun | 0 | 1 | 0 | 0 | 0 | 0 | 57 | 47
2026-09-21 | Mon | 0 | 0 | 0 | 0 | 1 | 1 | 58 | 48
2026-09-22 | Tue | 0 | 0 | 0 | 0 | 1 | 1 | 59 | 49
2026-09-23 | Wed | 0 | 0 | 0 | 0 | 1 | 1 | 60 | 50
2026-09-24 | Thu | 0 | 0 | 0 | 0 | 1 | 1 | 61 | 51
2026-09-25 | Fri | 0 | 0 | 0 | 0 | 1 | 1 | 62 | 52
2026-09-26 | Sat | 1 | 0 | 0 | 0 | 1 | 0 | 63 | 52
2026-09-27 | Sun | 0 | 1 | 0 | 0 | 0 | 0 | 63 | 52
2026-09-28 | Mon | 0 | 0 | 0 | 0 | 1 | 1 | 64 | 53
2026-09-29 | Tue | 0 | 0 | 0 | 0 | 1 | 1 | 65 | 54
2026-09-30 | Wed | 0 | 0 | 0 | 0 | 1 | 1 | 66 | 55
2026-10-01 | Thu | 0 | 0 | 0 | 0 | 1 | 1 | 67 | 56
2026-10-02 | Fri | 0 | 0 | 0 | 1 | 1 | 0 | 68 | 56
2026-10-03 | Sat | 1 | 0 | 0 | 0 | 1 | 0 | 69 | 56
2026-10-04 | Sun | 0 | 1 | 0 | 0 | 0 | 0 | 69 | 56
2026-10-05 | Mon | 0 | 0 | 0 | 0 | 1 | 1 | 70 | 57
2026-10-06 | Tue | 0 | 0 | 0 | 0 | 1 | 1 | 71 | 58
2026-10-07 | Wed | 0 | 0 | 0 | 0 | 1 | 1 | 72 | 59
2026-10-08 | Thu | 0 | 0 | 0 | 0 | 1 | 1 | 73 | 60
2026-10-09 | Fri | 0 | 0 | 0 | 0 | 1 | 1 | 74 | 61
2026-10-10 | Sat | 1 | 0 | 0 | 0 | 1 | 0 | 75 | 61
2026-10-11 | Sun | 0 | 1 | 0 | 0 | 0 | 0 | 75 | 61
2026-10-12 | Mon | 0 | 0 | 0 | 0 | 1 | 1 | 76 | 62
2026-10-13 | Tue | 0 | 0 | 0 | 0 | 1 | 1 | 77 | 63
2026-10-14 | Wed | 0 | 0 | 0 | 0 | 1 | 1 | 78 | 64
2026-10-15 | Thu | 0 | 0 | 0 | 0 | 1 | 1 | 79 | 65
2026-10-16 | Fri | 0 | 0 | 0 | 0 | 1 | 1 | 80 | 66
2026-10-17 | Sat | 1 | 0 | 0 | 0 | 1 | 0 | 81 | 66
2026-10-18 | Sun | 0 | 1 | 0 | 0 | 0 | 0 | 81 | 66
2026-10-19 | Mon | 0 | 0 | 0 | 0 | 1 | 1 | 82 | 67
2026-10-20 | Tue | 0 | 0 | 0 | 1 | 1 | 0 | 83 | 67
2026-10-21 | Wed | 0 | 0 | 0 | 0 | 1 | 1 | 84 | 68
2026-10-22 | Thu | 0 | 0 | 0 | 0 | 1 | 1 | 85 | 69
2026-10-23 | Fri | 0 | 0 | 0 | 0 | 1 | 1 | 86 | 70
2026-10-24 | Sat | 1 | 0 | 0 | 0 | 1 | 0 | 87 | 70
2026-10-25 | Sun | 0 | 1 | 0 | 0 | 0 | 0 | 87 | 70
2026-10-26 | Mon | 0 | 0 | 0 | 0 | 1 | 1 | 88 | 71
2026-10-27 | Tue | 0 | 0 | 0 | 0 | 1 | 1 | 89 | 72
2026-10-28 | Wed | 0 | 0 | 0 | 0 | 1 | 1 | 90 | 73
2026-10-29 | Thu | 0 | 0 | 0 | 0 | 1 | 1 | 91 | 74
2026-10-30 | Fri | 0 | 0 | 0 | 0 | 1 | 1 | 92 | 75
2026-10-31 | Sat | 1 | 0 | 0 | 0 | 1 | 0 | 93 | 75
2026-11-01 | Sun | 0 | 1 | 0 | 0 | 0 | 0 | 93 | 75
2026-11-02 | Mon | 0 | 0 | 0 | 0 | 1 | 1 | 94 | 76
2026-11-03 | Tue | 0 | 0 | 0 | 0 | 1 | 1 | 95 | 77
2026-11-04 | Wed | 0 | 0 | 0 | 0 | 1 | 1 | 96 | 78
2026-11-05 | Thu | 0 | 0 | 0 | 0 | 1 | 1 | 97 | 79
2026-11-06 | Fri | 0 | 0 | 0 | 0 | 1 | 1 | 98 | 80
2026-11-07 | Sat | 1 | 0 | 0 | 0 | 1 | 0 | 99 | 80
2026-11-08 | Sun | 0 | 1 | 0 | 0 | 0 | 0 | 99 | 80
2026-11-09 | Mon | 0 | 0 | 0 | 1 | 1 | 0 | 100 | 80
2026-11-10 | Tue | 0 | 0 | 0 | 0 | 1 | 1 | 101 | 81
2026-11-11 | Wed | 0 | 0 | 0 | 1 | 1 | 0 | 102 | 81
2026-11-12 | Thu | 0 | 0 | 0 | 0 | 1 | 1 | 103 | 82
2026-11-13 | Fri | 0 | 0 | 0 | 0 | 1 | 1 | 104 | 83
2026-11-14 | Sat | 1 | 0 | 0 | 0 | 1 | 0 | 105 | 83
2026-11-15 | Sun | 0 | 1 | 0 | 0 | 0 | 0 | 105 | 83
2026-11-16 | Mon | 0 | 0 | 0 | 0 | 1 | 1 | 106 | 84
2026-11-17 | Tue | 0 | 0 | 0 | 0 | 1 | 1 | 107 | 85
2026-11-18 | Wed | 0 | 0 | 0 | 0 | 1 | 1 | 108 | 86
2026-11-19 | Thu | 0 | 0 | 0 | 0 | 1 | 1 | 109 | 87
2026-11-20 | Fri | 0 | 0 | 0 | 0 | 1 | 1 | 110 | 88
2026-11-21 | Sat | 1 | 0 | 0 | 0 | 1 | 0 | 111 | 88
2026-11-22 | Sun | 0 | 1 | 0 | 0 | 0 | 0 | 111 | 88
2026-11-23 | Mon | 0 | 0 | 0 | 0 | 1 | 1 | 112 | 89
2026-11-24 | Tue | 0 | 0 | 0 | 1 | 1 | 0 | 113 | 89
2026-11-25 | Wed | 0 | 0 | 0 | 0 | 1 | 1 | 114 | 90
2026-11-26 | Thu | 0 | 0 | 0 | 0 | 1 | 1 | 115 | 91
2026-11-27 | Fri | 0 | 0 | 0 | 0 | 1 | 1 | 116 | 92
2026-11-28 | Sat | 1 | 0 | 0 | 0 | 1 | 0 | 117 | 92
2026-11-29 | Sun | 0 | 1 | 0 | 0 | 0 | 0 | 117 | 92
2026-11-30 | Mon | 0 | 0 | 0 | 0 | 1 | 1 | 118 | 93
2026-12-01 | Tue | 0 | 0 | 0 | 0 | 1 | 1 | 119 | 94
2026-12-02 | Wed | 0 | 0 | 0 | 0 | 1 | 1 | 120 | 95
2026-12-03 | Thu | 0 | 0 | 0 | 0 | 1 | 1 | 121 | 96
2026-12-04 | Fri | 0 | 0 | 0 | 0 | 1 | 1 | 122 | 97
2026-12-05 | Sat | 1 | 0 | 0 | 0 | 1 | 0 | 123 | 97
2026-12-06 | Sun | 0 | 1 | 0 | 0 | 0 | 0 | 123 | 97
2026-12-07 | Mon | 0 | 0 | 0 | 0 | 1 | 1 | 124 | 98
2026-12-08 | Tue | 0 | 0 | 0 | 0 | 1 | 1 | 125 | 99
2026-12-09 | Wed | 0 | 0 | 0 | 0 | 1 | 1 | 126 | 100
2026-12-10 | Thu | 0 | 0 | 0 | 0 | 1 | 1 | 127 | 101
2026-12-11 | Fri | 0 | 0 | 0 | 0 | 1 | 1 | 128 | 102
2026-12-12 | Sat | 1 | 0 | 0 | 0 | 1 | 0 | 129 | 102
2026-12-13 | Sun | 0 | 1 | 0 | 0 | 0 | 0 | 129 | 102
2026-12-14 | Mon | 0 | 0 | 0 | 0 | 1 | 1 | 130 | 103
2026-12-15 | Tue | 0 | 0 | 0 | 0 | 1 | 1 | 131 | 104
2026-12-16 | Wed | 0 | 0 | 0 | 0 | 1 | 1 | 132 | 105
2026-12-17 | Thu | 0 | 0 | 0 | 0 | 1 | 1 | 133 | 106
2026-12-18 | Fri | 0 | 0 | 0 | 0 | 1 | 1 | 134 | 107
2026-12-19 | Sat | 1 | 0 | 0 | 0 | 1 | 0 | 135 | 107
2026-12-20 | Sun | 0 | 1 | 0 | 0 | 0 | 0 | 135 | 107
2026-12-21 | Mon | 0 | 0 | 0 | 0 | 1 | 1 | 136 | 108
2026-12-22 | Tue | 0 | 0 | 0 | 0 | 1 | 1 | 137 | 109
2026-12-23 | Wed | 0 | 0 | 0 | 0 | 1 | 1 | 138 | 110
2026-12-24 | Thu | 0 | 0 | 0 | 0 | 1 | 1 | 139 | 111
2026-12-25 | Fri | 0 | 0 | 0 | 1 | 1 | 0 | 140 | 111
2026-12-26 | Sat | 1 | 0 | 0 | 0 | 1 | 0 | 141 | 111
2026-12-27 | Sun | 0 | 1 | 0 | 0 | 0 | 0 | 141 | 111
2026-12-28 | Mon | 0 | 0 | 0 | 0 | 1 | 1 | 142 | 112
2026-12-29 | Tue | 0 | 0 | 0 | 0 | 1 | 1 | 143 | 113
2026-12-30 | Wed | 0 | 0 | 0 | 0 | 1 | 1 | 144 | 114
2026-12-31 | Thu | 0 | 0 | 0 | 0 | 1 | 1 | 145 | 115
2027-01-01 | Fri | 0 | 0 | 0 | 0 | 1 | 1 | 146 | 116
2027-01-02 | Sat | 1 | 0 | 0 | 0 | 1 | 0 | 147 | 116
2027-01-03 | Sun | 0 | 1 | 0 | 0 | 0 | 0 | 147 | 116
2027-01-04 | Mon | 0 | 0 | 0 | 0 | 1 | 1 | 148 | 117
2027-01-05 | Tue | 0 | 0 | 0 | 0 | 1 | 1 | 149 | 118
2027-01-06 | Wed | 0 | 0 | 0 | 0 | 1 | 1 | 150 | 119
2027-01-07 | Thu | 0 | 0 | 0 | 0 | 1 | 1 | 151 | 120
2027-01-08 | Fri | 0 | 0 | 0 | 0 | 1 | 1 | 152 | 121
2027-01-09 | Sat | 1 | 0 | 0 | 0 | 1 | 0 | 153 | 121
2027-01-10 | Sun | 0 | 1 | 0 | 0 | 0 | 0 | 153 | 121
2027-01-11 | Mon | 0 | 0 | 0 | 0 | 1 | 1 | 154 | 122
2027-01-12 | Tue | 0 | 0 | 0 | 0 | 1 | 1 | 155 | 123
2027-01-13 | Wed | 0 | 0 | 0 | 0 | 1 | 1 | 156 | 124
2027-01-14 | Thu | 0 | 0 | 0 | 0 | 1 | 1 | 157 | 125
2027-01-15 | Fri | 0 | 0 | 0 | 0 | 1 | 1 | 158 | 126
2027-01-16 | Sat | 1 | 0 | 0 | 0 | 1 | 0 | 159 | 126
2027-01-17 | Sun | 0 | 1 | 0 | 0 | 0 | 0 | 159 | 126
2027-01-18 | Mon | 0 | 0 | 0 | 0 | 1 | 1 | 160 | 127
2027-01-19 | Tue | 0 | 0 | 0 | 0 | 1 | 1 | 161 | 128
2027-01-20 | Wed | 0 | 0 | 0 | 0 | 1 | 1 | 162 | 129
2027-01-21 | Thu | 0 | 0 | 0 | 0 | 1 | 1 | 163 | 130
2027-01-22 | Fri | 0 | 0 | 0 | 0 | 1 | 1 | 164 | 131
2027-01-23 | Sat | 1 | 0 | 0 | 0 | 1 | 0 | 165 | 131
2027-01-24 | Sun | 0 | 1 | 0 | 0 | 0 | 0 | 165 | 131
2027-01-25 | Mon | 0 | 0 | 0 | 0 | 1 | 1 | 166 | 132
2027-01-26 | Tue | 0 | 0 | 0 | 0 | 1 | 1 | 167 | 133
2027-01-27 | Wed | 0 | 0 | 0 | 0 | 1 | 1 | 168 | 134
2027-01-28 | Thu | 0 | 0 | 0 | 0 | 1 | 1 | 169 | 135
2027-01-29 | Fri | 0 | 0 | 0 | 0 | 1 | 1 | 170 | 136
2027-01-30 | Sat | 1 | 0 | 0 | 0 | 1 | 0 | 171 | 136
2027-01-31 | Sun | 0 | 1 | 0 | 0 | 0 | 0 | 171 | 136
2027-02-01 | Mon | 0 | 0 | 0 | 0 | 1 | 1 | 172 | 137
2027-02-02 | Tue | 0 | 0 | 0 | 0 | 1 | 1 | 173 | 138
2027-02-03 | Wed | 0 | 0 | 0 | 0 | 1 | 1 | 174 | 139
2027-02-04 | Thu | 0 | 0 | 0 | 0 | 1 | 1 | 175 | 140
2027-02-05 | Fri | 0 | 0 | 0 | 0 | 1 | 1 | 176 | 141
2027-02-06 | Sat | 1 | 0 | 0 | 0 | 1 | 0 | 177 | 141
2027-02-07 | Sun | 0 | 1 | 0 | 0 | 0 | 0 | 177 | 141
2027-02-08 | Mon | 0 | 0 | 0 | 0 | 1 | 1 | 178 | 142
2027-02-09 | Tue | 0 | 0 | 0 | 0 | 1 | 1 | 179 | 143
2027-02-10 | Wed | 0 | 0 | 0 | 0 | 1 | 1 | 180 | 144
2027-02-11 | Thu | 0 | 0 | 0 | 0 | 1 | 1 | 181 | 145
2027-02-12 | Fri | 0 | 0 | 0 | 0 | 1 | 1 | 182 | 146
2027-02-13 | Sat | 1 | 0 | 0 | 0 | 1 | 0 | 183 | 146
2027-02-14 | Sun | 0 | 1 | 0 | 0 | 0 | 0 | 183 | 146
2027-02-15 | Mon | 0 | 0 | 0 | 0 | 1 | 1 | 184 | 147
2027-02-16 | Tue | 0 | 0 | 0 | 0 | 1 | 1 | 185 | 148
2027-02-17 | Wed | 0 | 0 | 0 | 0 | 1 | 1 | 186 | 149
2027-02-18 | Thu | 0 | 0 | 0 | 0 | 1 | 1 | 187 | 150
2027-02-19 | Fri | 0 | 0 | 0 | 0 | 1 | 1 | 188 | 151
2027-02-20 | Sat | 1 | 0 | 0 | 0 | 1 | 0 | 189 | 151
2027-02-21 | Sun | 0 | 1 | 0 | 0 | 0 | 0 | 189 | 151
2027-02-22 | Mon | 0 | 0 | 0 | 0 | 1 | 1 | 190 | 152
2027-02-23 | Tue | 0 | 0 | 0 | 0 | 1 | 1 | 191 | 153
2027-02-24 | Wed | 0 | 0 | 0 | 0 | 1 | 1 | 192 | 154
2027-02-25 | Thu | 0 | 0 | 0 | 0 | 1 | 1 | 193 | 155
2027-02-26 | Fri | 0 | 0 | 0 | 0 | 1 | 1 | 194 | 156
2027-02-27 | Sat | 1 | 0 | 0 | 0 | 1 | 0 | 195 | 156
2027-02-28 | Sun | 0 | 1 | 0 | 0 | 0 | 0 | 195 | 156
2027-03-01 | Mon | 0 | 0 | 0 | 0 | 1 | 1 | 196 | 157
2027-03-02 | Tue | 0 | 0 | 0 | 0 | 1 | 1 | 197 | 158
2027-03-03 | Wed | 0 | 0 | 0 | 0 | 1 | 1 | 198 | 159
2027-03-04 | Thu | 0 | 0 | 0 | 0 | 1 | 1 | 199 | 160
2027-03-05 | Fri | 0 | 0 | 0 | 0 | 1 | 1 | 200 | 161
2027-03-06 | Sat | 1 | 0 | 0 | 0 | 1 | 0 | 201 | 161
2027-03-07 | Sun | 0 | 1 | 0 | 0 | 0 | 0 | 201 | 161
2027-03-08 | Mon | 0 | 0 | 0 | 0 | 1 | 1 | 202 | 162
2027-03-09 | Tue | 0 | 0 | 0 | 0 | 1 | 1 | 203 | 163
2027-03-10 | Wed | 0 | 0 | 0 | 0 | 1 | 1 | 204 | 164
2027-03-11 | Thu | 0 | 0 | 0 | 0 | 1 | 1 | 205 | 165
2027-03-12 | Fri | 0 | 0 | 0 | 0 | 1 | 1 | 206 | 166
2027-03-13 | Sat | 1 | 0 | 0 | 0 | 1 | 0 | 207 | 166
2027-03-14 | Sun | 0 | 1 | 0 | 0 | 0 | 0 | 207 | 166
2027-03-15 | Mon | 0 | 0 | 0 | 0 | 1 | 1 | 208 | 167
2027-03-16 | Tue | 0 | 0 | 0 | 0 | 1 | 1 | 209 | 168
2027-03-17 | Wed | 0 | 0 | 0 | 0 | 1 | 1 | 210 | 169
2027-03-18 | Thu | 0 | 0 | 0 | 0 | 1 | 1 | 211 | 170
2027-03-19 | Fri | 0 | 0 | 0 | 0 | 1 | 1 | 212 | 171
2027-03-20 | Sat | 1 | 0 | 0 | 0 | 1 | 0 | 213 | 171
2027-03-21 | Sun | 0 | 1 | 0 | 0 | 0 | 0 | 213 | 171
2027-03-22 | Mon | 0 | 0 | 0 | 0 | 1 | 1 | 214 | 172
2027-03-23 | Tue | 0 | 0 | 0 | 0 | 1 | 1 | 215 | 173
2027-03-24 | Wed | 0 | 0 | 0 | 0 | 1 | 1 | 216 | 174
2027-03-25 | Thu | 0 | 0 | 0 | 0 | 1 | 1 | 217 | 175
2027-03-26 | Fri | 0 | 0 | 0 | 0 | 1 | 1 | 218 | 176
2027-03-27 | Sat | 1 | 0 | 0 | 0 | 1 | 0 | 219 | 176
2027-03-28 | Sun | 0 | 1 | 0 | 0 | 0 | 0 | 219 | 176
2027-03-29 | Mon | 0 | 0 | 0 | 0 | 1 | 1 | 220 | 177
2027-03-30 | Tue | 0 | 0 | 0 | 0 | 1 | 1 | 221 | 178
2027-03-31 | Wed | 0 | 0 | 0 | 0 | 1 | 1 | 222 | 179
2027-04-01 | Thu | 0 | 0 | 0 | 0 | 1 | 1 | 223 | 180
2027-04-02 | Fri | 0 | 0 | 0 | 0 | 1 | 1 | 224 | 181
2027-04-03 | Sat | 1 | 0 | 0 | 0 | 1 | 0 | 225 | 181
2027-04-04 | Sun | 0 | 1 | 0 | 0 | 0 | 0 | 225 | 181
2027-04-05 | Mon | 0 | 0 | 0 | 0 | 1 | 1 | 226 | 182
2027-04-06 | Tue | 0 | 0 | 0 | 0 | 1 | 1 | 227 | 183
2027-04-07 | Wed | 0 | 0 | 0 | 0 | 1 | 1 | 228 | 184
2027-04-08 | Thu | 0 | 0 | 0 | 0 | 1 | 1 | 229 | 185
2027-04-09 | Fri | 0 | 0 | 0 | 0 | 1 | 1 | 230 | 186
2027-04-10 | Sat | 1 | 0 | 0 | 0 | 1 | 0 | 231 | 186
2027-04-11 | Sun | 0 | 1 | 0 | 0 | 0 | 0 | 231 | 186
2027-04-12 | Mon | 0 | 0 | 0 | 0 | 1 | 1 | 232 | 187
2027-04-13 | Tue | 0 | 0 | 0 | 0 | 1 | 1 | 233 | 188
2027-04-14 | Wed | 0 | 0 | 0 | 0 | 1 | 1 | 234 | 189
2027-04-15 | Thu | 0 | 0 | 0 | 0 | 1 | 1 | 235 | 190
2027-04-16 | Fri | 0 | 0 | 0 | 0 | 1 | 1 | 236 | 191
2027-04-17 | Sat | 1 | 0 | 0 | 0 | 1 | 0 | 237 | 191
2027-04-18 | Sun | 0 | 1 | 0 | 0 | 0 | 0 | 237 | 191
2027-04-19 | Mon | 0 | 0 | 0 | 0 | 1 | 1 | 238 | 192
2027-04-20 | Tue | 0 | 0 | 0 | 0 | 1 | 1 | 239 | 193
2027-04-21 | Wed | 0 | 0 | 0 | 0 | 1 | 1 | 240 | 194
2027-04-22 | Thu | 0 | 0 | 0 | 0 | 1 | 1 | 241 | 195
2027-04-23 | Fri | 0 | 0 | 0 | 0 | 1 | 1 | 242 | 196
2027-04-24 | Sat | 1 | 0 | 0 | 0 | 1 | 0 | 243 | 196
2027-04-25 | Sun | 0 | 1 | 0 | 0 | 0 | 0 | 243 | 196
2027-04-26 | Mon | 0 | 0 | 0 | 0 | 1 | 1 | 244 | 197
2027-04-27 | Tue | 0 | 0 | 0 | 0 | 1 | 1 | 245 | 198
2027-04-28 | Wed | 0 | 0 | 0 | 0 | 1 | 1 | 246 | 199
2027-04-29 | Thu | 0 | 0 | 0 | 0 | 1 | 1 | 247 | 200
2027-04-30 | Fri | 0 | 0 | 0 | 0 | 1 | 1 | 248 | 201
2027-05-01 | Sat | 1 | 0 | 0 | 0 | 1 | 0 | 249 | 201
2027-05-02 | Sun | 0 | 1 | 0 | 0 | 0 | 0 | 249 | 201
2027-05-03 | Mon | 0 | 0 | 0 | 0 | 1 | 1 | 250 | 202
2027-05-04 | Tue | 0 | 0 | 0 | 0 | 1 | 1 | 251 | 203
2027-05-05 | Wed | 0 | 0 | 0 | 0 | 1 | 1 | 252 | 204
2027-05-06 | Thu | 0 | 0 | 0 | 0 | 1 | 1 | 253 | 205
2027-05-07 | Fri | 0 | 0 | 0 | 0 | 1 | 1 | 254 | 206
2027-05-08 | Sat | 1 | 0 | 0 | 0 | 1 | 0 | 255 | 206
2027-05-09 | Sun | 0 | 1 | 0 | 0 | 0 | 0 | 255 | 206
2027-05-10 | Mon | 0 | 0 | 0 | 0 | 1 | 1 | 256 | 207
2027-05-11 | Tue | 0 | 0 | 0 | 0 | 1 | 1 | 257 | 208
2027-05-12 | Wed | 0 | 0 | 0 | 0 | 1 | 1 | 258 | 209
2027-05-13 | Thu | 0 | 0 | 0 | 0 | 1 | 1 | 259 | 210
2027-05-14 | Fri | 0 | 0 | 0 | 0 | 1 | 1 | 260 | 211
2027-05-15 | Sat | 1 | 0 | 0 | 0 | 1 | 0 | 261 | 211
2027-05-16 | Sun | 0 | 1 | 0 | 0 | 0 | 0 | 261 | 211
2027-05-17 | Mon | 0 | 0 | 0 | 0 | 1 | 1 | 262 | 212
2027-05-18 | Tue | 0 | 0 | 0 | 0 | 1 | 1 | 263 | 213
2027-05-19 | Wed | 0 | 0 | 0 | 0 | 1 | 1 | 264 | 214
2027-05-20 | Thu | 0 | 0 | 0 | 0 | 1 | 1 | 265 | 215
2027-05-21 | Fri | 0 | 0 | 0 | 0 | 1 | 1 | 266 | 216
2027-05-22 | Sat | 1 | 0 | 0 | 0 | 1 | 0 | 267 | 216
2027-05-23 | Sun | 0 | 1 | 0 | 0 | 0 | 0 | 267 | 216
2027-05-24 | Mon | 0 | 0 | 0 | 0 | 1 | 1 | 268 | 217
2027-05-25 | Tue | 0 | 0 | 0 | 0 | 1 | 1 | 269 | 218
2027-05-26 | Wed | 0 | 0 | 0 | 0 | 1 | 1 | 270 | 219
2027-05-27 | Thu | 0 | 0 | 0 | 0 | 1 | 1 | 271 | 220
2027-05-28 | Fri | 0 | 0 | 0 | 0 | 1 | 1 | 272 | 221
2027-05-29 | Sat | 1 | 0 | 0 | 0 | 1 | 0 | 273 | 221
2027-05-30 | Sun | 0 | 1 | 0 | 0 | 0 | 0 | 273 | 221
2027-05-31 | Mon | 0 | 0 | 0 | 0 | 1 | 1 | 274 | 222
2027-06-01 | Tue | 0 | 0 | 0 | 0 | 1 | 1 | 275 | 223
2027-06-02 | Wed | 0 | 0 | 0 | 0 | 1 | 1 | 276 | 224
2027-06-03 | Thu | 0 | 0 | 0 | 0 | 1 | 1 | 277 | 225
2027-06-04 | Fri | 0 | 0 | 0 | 0 | 1 | 1 | 278 | 226
2027-06-05 | Sat | 1 | 0 | 0 | 0 | 1 | 0 | 279 | 226
2027-06-06 | Sun | 0 | 1 | 0 | 0 | 0 | 0 | 279 | 226
2027-06-07 | Mon | 0 | 0 | 0 | 0 | 1 | 1 | 280 | 227
2027-06-08 | Tue | 0 | 0 | 0 | 0 | 1 | 1 | 281 | 228
2027-06-09 | Wed | 0 | 0 | 0 | 0 | 1 | 1 | 282 | 229
2027-06-10 | Thu | 0 | 0 | 0 | 0 | 1 | 1 | 283 | 230
2027-06-11 | Fri | 0 | 0 | 0 | 0 | 1 | 1 | 284 | 231
2027-06-12 | Sat | 1 | 0 | 0 | 0 | 1 | 0 | 285 | 231
2027-06-13 | Sun | 0 | 1 | 0 | 0 | 0 | 0 | 285 | 231
2027-06-14 | Mon | 0 | 0 | 0 | 0 | 1 | 1 | 286 | 232
2027-06-15 | Tue | 0 | 0 | 0 | 0 | 1 | 1 | 287 | 233
2027-06-16 | Wed | 0 | 0 | 0 | 0 | 1 | 1 | 288 | 234
2027-06-17 | Thu | 0 | 0 | 0 | 0 | 1 | 1 | 289 | 235
2027-06-18 | Fri | 0 | 0 | 0 | 0 | 1 | 1 | 290 | 236
2027-06-19 | Sat | 1 | 0 | 0 | 0 | 1 | 0 | 291 | 236
2027-06-20 | Sun | 0 | 1 | 0 | 0 | 0 | 0 | 291 | 236
2027-06-21 | Mon | 0 | 0 | 0 | 0 | 1 | 1 | 292 | 237
2027-06-22 | Tue | 0 | 0 | 0 | 0 | 1 | 1 | 293 | 238
2027-06-23 | Wed | 0 | 0 | 0 | 0 | 1 | 1 | 294 | 239
2027-06-24 | Thu | 0 | 0 | 0 | 0 | 1 | 1 | 295 | 240
2027-06-25 | Fri | 0 | 0 | 0 | 0 | 1 | 1 | 296 | 241
2027-06-26 | Sat | 1 | 0 | 0 | 0 | 1 | 0 | 297 | 241
2027-06-27 | Sun | 0 | 1 | 0 | 0 | 0 | 0 | 297 | 241
2027-06-28 | Mon | 0 | 0 | 0 | 0 | 1 | 1 | 298 | 242
2027-06-29 | Tue | 0 | 0 | 0 | 0 | 1 | 1 | 299 | 243
2027-06-30 | Wed | 0 | 0 | 0 | 0 | 1 | 1 | 300 | 244
2027-07-01 | Thu | 0 | 0 | 0 | 0 | 1 | 1 | 301 | 245
2027-07-02 | Fri | 0 | 0 | 0 | 0 | 1 | 1 | 302 | 246
2027-07-03 | Sat | 1 | 0 | 0 | 0 | 1 | 0 | 303 | 246
2027-07-04 | Sun | 0 | 1 | 0 | 0 | 0 | 0 | 303 | 246
2027-07-05 | Mon | 0 | 0 | 0 | 0 | 1 | 1 | 304 | 247
2027-07-06 | Tue | 0 | 0 | 0 | 0 | 1 | 1 | 305 | 248
2027-07-07 | Wed | 0 | 0 | 0 | 0 | 1 | 1 | 306 | 249
2027-07-08 | Thu | 0 | 0 | 0 | 0 | 1 | 1 | 307 | 250
2027-07-09 | Fri | 0 | 0 | 0 | 0 | 1 | 1 | 308 | 251
2027-07-10 | Sat | 1 | 0 | 0 | 0 | 1 | 0 | 309 | 251
2027-07-11 | Sun | 0 | 1 | 0 | 0 | 0 | 0 | 309 | 251
2027-07-12 | Mon | 0 | 0 | 0 | 0 | 1 | 1 | 310 | 252
2027-07-13 | Tue | 0 | 0 | 0 | 0 | 1 | 1 | 311 | 253
2027-07-14 | Wed | 0 | 0 | 0 | 0 | 1 | 1 | 312 | 254
2027-07-15 | Thu | 0 | 0 | 0 | 0 | 1 | 1 | 313 | 255
2027-07-16 | Fri | 0 | 0 | 0 | 0 | 1 | 1 | 314 | 256
2027-07-17 | Sat | 1 | 0 | 0 | 0 | 1 | 0 | 315 | 256
2027-07-18 | Sun | 0 | 1 | 0 | 0 | 0 | 0 | 315 | 256
2027-07-19 | Mon | 0 | 0 | 0 | 0 | 1 | 1 | 316 | 257
2027-07-20 | Tue | 0 | 0 | 0 | 0 | 1 | 1 | 317 | 258
2027-07-21 | Wed | 0 | 0 | 0 | 0 | 1 | 1 | 318 | 259
2027-07-22 | Thu | 0 | 0 | 0 | 0 | 1 | 1 | 319 | 260
2027-07-23 | Fri | 0 | 0 | 0 | 0 | 1 | 1 | 320 | 261
2027-07-24 | Sat | 1 | 0 | 0 | 0 | 1 | 0 | 321 | 261
2027-07-25 | Sun | 0 | 1 | 0 | 0 | 0 | 0 | 321 | 261
2027-07-26 | Mon | 0 | 0 | 0 | 0 | 1 | 1 | 322 | 262
2027-07-27 | Tue | 0 | 0 | 0 | 0 | 1 | 1 | 323 | 263
2027-07-28 | Wed | 0 | 0 | 0 | 0 | 1 | 1 | 324 | 264
2027-07-29 | Thu | 0 | 0 | 0 | 0 | 1 | 1 | 325 | 265
2027-07-30 | Fri | 0 | 0 | 0 | 0 | 1 | 1 | 326 | 266
2027-07-31 | Sat | 1 | 0 | 0 | 0 | 1 | 0 | 327 | 266
2027-08-01 | Sun | 0 | 1 | 0 | 0 | 0 | 0 | 327 | 266
2027-08-02 | Mon | 0 | 0 | 0 | 0 | 1 | 1 | 328 | 267
2027-08-03 | Tue | 0 | 0 | 0 | 0 | 1 | 1 | 329 | 268
2027-08-04 | Wed | 0 | 0 | 0 | 0 | 1 | 1 | 330 | 269
2027-08-05 | Thu | 0 | 0 | 0 | 0 | 1 | 1 | 331 | 270
2027-08-06 | Fri | 0 | 0 | 0 | 0 | 1 | 1 | 332 | 271
2027-08-07 | Sat | 1 | 0 | 0 | 0 | 1 | 0 | 333 | 271
2027-08-08 | Sun | 0 | 1 | 0 | 0 | 0 | 0 | 333 | 271
2027-08-09 | Mon | 0 | 0 | 0 | 0 | 1 | 1 | 334 | 272
2027-08-10 | Tue | 0 | 0 | 0 | 0 | 1 | 1 | 335 | 273
2027-08-11 | Wed | 0 | 0 | 0 | 0 | 1 | 1 | 336 | 274
2027-08-12 | Thu | 0 | 0 | 0 | 0 | 1 | 1 | 337 | 275
2027-08-13 | Fri | 0 | 0 | 0 | 0 | 1 | 1 | 338 | 276
2027-08-14 | Sat | 1 | 0 | 0 | 0 | 1 | 0 | 339 | 276
2027-08-15 | Sun | 0 | 1 | 0 | 0 | 0 | 0 | 339 | 276
2027-08-16 | Mon | 0 | 0 | 0 | 0 | 1 | 1 | 340 | 277
2027-08-17 | Tue | 0 | 0 | 0 | 0 | 1 | 1 | 341 | 278
2027-08-18 | Wed | 0 | 0 | 0 | 0 | 1 | 1 | 342 | 279
2027-08-19 | Thu | 0 | 0 | 0 | 0 | 1 | 1 | 343 | 280
2027-08-20 | Fri | 0 | 0 | 0 | 0 | 1 | 1 | 344 | 281
2027-08-21 | Sat | 1 | 0 | 0 | 0 | 1 | 0 | 345 | 281
2027-08-22 | Sun | 0 | 1 | 0 | 0 | 0 | 0 | 345 | 281
2027-08-23 | Mon | 0 | 0 | 0 | 0 | 1 | 1 | 346 | 282
2027-08-24 | Tue | 0 | 0 | 0 | 0 | 1 | 1 | 347 | 283
2027-08-25 | Wed | 0 | 0 | 0 | 0 | 1 | 1 | 348 | 284
2027-08-26 | Thu | 0 | 0 | 0 | 0 | 1 | 1 | 349 | 285
2027-08-27 | Fri | 0 | 0 | 0 | 0 | 1 | 1 | 350 | 286
2027-08-28 | Sat | 1 | 0 | 0 | 0 | 1 | 0 | 351 | 286
2027-08-29 | Sun | 0 | 1 | 0 | 0 | 0 | 0 | 351 | 286
2027-08-30 | Mon | 0 | 0 | 0 | 0 | 1 | 1 | 352 | 287
2027-08-31 | Tue | 0 | 0 | 0 | 0 | 1 | 1 | 353 | 288
2027-09-01 | Wed | 0 | 0 | 0 | 0 | 1 | 1 | 354 | 289
2027-09-02 | Thu | 0 | 0 | 0 | 0 | 1 | 1 | 355 | 290
2027-09-03 | Fri | 0 | 0 | 0 | 0 | 1 | 1 | 356 | 291
2027-09-04 | Sat | 1 | 0 | 0 | 0 | 1 | 0 | 357 | 291
2027-09-05 | Sun | 0 | 1 | 0 | 0 | 0 | 0 | 357 | 291
2027-09-06 | Mon | 0 | 0 | 0 | 0 | 1 | 1 | 358 | 292
2027-09-07 | Tue | 0 | 0 | 0 | 0 | 1 | 1 | 359 | 293
Formulas:
Date = [Date, row above]+1