## Slide 1
TRIPLE-C · NAVFARM IMPLEMENTATION
Project Management Team
Kick-Off Meeting
Date: 04 August 2026, 11:15 Chair: Group Finance Director, Triple-C Duration: 60 minutes
Prepared by Prudence Consulting for Triple-C

## Slide 2
Meeting Agenda
1
Welcome & Introductions
GFD
2
Project Goals & Implementation Methodology
Prudence
3
Project Scope and Deliverables
Prudence
4
Implementation Roadmap and Milestones
Prudence
5
Roles, Governance and Communication
GFD
6
Operational Considerations and Risk Management
Johan / John
7
Resource Allocation & Organisational Change Management
GFD
8
Immediate Next Steps
Prudence
9
Any Other Business (AOB)
All
Triple-C | NAVFARM Implementation - PMT Kick-Off Meeting
1

## Slide 3
Project Vision & Business Case
Group Finance Director
What we are trying to do
Move Triple-C's pig farms away from paper and spreadsheets and onto one digital system (NAVFarm), linked to our finance system (D365 Business Central). This gives everyone, from farm level to head office, the same accurate, real-time picture of the herd, feed and money.
Why this matters now
Manual tracking makes it hard to know true feed cost and pig profitability
There is no standard way to value the herd for financial reporting, in real time
Farm data is scattered across different books, cards and sheets
Farm-level ERP access is expensive and rarely fully used
Project Objectives
Digitise farm operations end-to-end with NAVFarm
Automate the pig herd's financial valuation inside D365BC
Give real-time visibility of feed use, pig lifecycle and profit
Reduce ERP licence costs with a low-cost farm user model
Build the foundation for future IoT-enabled smart farming
Triple-C | NAVFARM Implementation - PMT Kick-Off Meeting
2

## Slide 4
Where We Are Today vs. Where We Are Going
Group Finance Director
Today (Current State)
Feed use tracked manually
No standard way to value pigs for accounts, on real time
Heavy, costly ERP use required at farm level
Farm data spread across many separate sources
Limited visibility of profit - no real-time picture
Animal health tracked manually, farm by farm
Tomorrow (Future State)
Fully digital farm operations through NAVFarm
Automatic pig valuation inside D365BC
Real-time feed cost and lifecycle tracking
Automatic alerts and notifications
One historical record for year-on-year comparison
Low-cost licensing model + RFID smart farm tools
Offline data capture available at farm level
Triple-C | NAVFARM Implementation - PMT Kick-Off Meeting
3

## Slide 5
How the Solution Fits Together
In simple terms
1. NAVFarm App
Farm teams record feed, health, weights and RFID scans, on the web or mobile, even offline.
→
2. NAVFarm Connector
Automatically and securely sends that farm data to the finance system in real time.
→
3. D365 Business Central
Keeps the financial books, and automatically values the pig herd as a 'biological asset'.
→
4. Reports & Dashboards
Management gets one accurate, real-time view of the herd, costs and profitability.
Also: NAVFarm exchanges data with the Pig Vision application (breeding, growth, health records) via APIs, so the same information never needs to be typed in twice.
Looking ahead (Phase 2): water meters, silo weight scales and other sensors can be connected to NAVFarm for fully automated readings.
Triple-C | NAVFARM Implementation - PMT Kick-Off Meeting
4

## Slide 6
Project Management Team - Triple-C (1 of 2)
Group Finance Director
S. No. | Name | Title | Project Role
1 | Mandy Murebwa | Group Finance Director | Project Management Chairperson
2 | Hama Mudavose | Group ICT Executive | Project Management Role
3 | Johan Odendaal | General Manager | Farm Operations Implementation Lead
4 | Innocent Sithole | Group Financial Manager | Financial Controls
5 | John Nyabadza | Finance Manager | Finance Lead Role - Triple-C
6 | Israel Muchuchu | Human Resources Manager | Human Capital Resource Management
7 | Lara Baum | Farm Manager - Multiplier | Farm Operations (Multiplier)
8 | Ngoni Dedza | Mill Manager | Milling Operations - Transfer Orders
9 | Jimmyson Kazangarare | Farm Manager - Porta | Farm Operations (Porta)
10 | Solomon Maposa | Farm Manager - Richlands | Farm Operations (Richlands)
11 | Archbald Gwebere | Data Analyst | Data Analyst - Farming Operations
Triple-C | NAVFARM Implementation - PMT Kick-Off Meeting
5

## Slide 7
Project Management Team - Triple-C (2 of 2)
Group Finance Director
S. No. | Name | Title | Project Role
12 | Tafadzwa Katsokore | Farm Supervisor | Lions Head Farm Operations
13 | Willis Mudzonga | Farm Supervisor | Villa Franca Farm Operations
14 | Trevor Mudimu | Farm Supervisor | Learig Farm Operations
15 | Runyararo Sithole | ICT Systems Administrator | ICT Technical Implementation - Triple-C
16 | David Zvinoitavamwe | ICT Manager | ICT Technical Implementation
17 | Tonderai Gonamombe | Management Accountant | Costing Role
18 | Fungai Sigauke | Site Manager - Learig | Farm Operations (Learig)
19 | Gerd Baum | Farm Manager - Grasmere | Farm Operations (Grasmere)
20 | Johan Fourie | Farm Manager - LionHead | Farm Operations (LionHead)
21 | Tapiwa Mupambuzi | Farm Manager - Villa Franca | Farm Operations (Villa Franca)
Triple-C | NAVFARM Implementation - PMT Kick-Off Meeting
6

## Slide 8
Project Management Team - Prudence Consulting
Implementation Partner
S. No. | Name | Title | Project Role
1 | Abhinav Singh | Operation Director | Project Steering Committee Chairperson
2 | Neha Rawat | PMO | Project Management Role
3 | Paul Young | Product Manager | Project Manager
4 | Mukul Joshi | Senior Solution Architect | Solution Designer
5 | Anshu | Functional Consultant & Trainer | Functional Consultant & Trainer
6 | Rishi | Technical | Front-End Developer
7 | Arun | Technical | Back-End Developer
Triple-C | NAVFARM Implementation - PMT Kick-Off Meeting
7

## Slide 9
Project Goals & Business Value
Prudence Consulting
Project Goals
Fully digital farm operations via NAVFarm
Automated biological asset valuation in D365BC
Real-time feed and lifecycle tracking, with alerts
Optimised, low-cost farm licensing model
Integrated RFID smart farm ecosystem
Business Value by Area
Area | Expected Impact
ERP Licence Cost | Significant reduction
Feed Cost Control | Optimised consumption
Asset Valuation | Automated & accurate
Operational Control | Real-time farm visibility
Decision Making | Data-driven MIS dashboards
Triple-C | NAVFARM Implementation - PMT Kick-Off Meeting
8

## Slide 10
Key Capabilities (1 of 2)
What NAVFarm delivers for Triple-C's farms
1. Production Excellence
End-to-end lifecycle: breeding → farrowing → grow-out
Housing and feeding managed by stage
Focus on productivity: litter size, growth rates
2. Animal Health & Biosecurity
Vaccination and disease control tracking
Mortality reduction and herd health monitoring
3. Integrated Operations Control
Batch tracking across locations and sheds
Full animal movement tracking
4. Financial & Data Intelligence
Cost control: feed, amortisation, operations
KPI tracking: FCR, cost per piglet, performance
Real-time ERP dashboards in NAVFarm
Triple-C | NAVFARM Implementation - PMT Kick-Off Meeting
9

## Slide 11
Key Capabilities (2 of 2)
How NAVFarm tracks cost & value, built for gilt, boar and semen costing
Imported & Local Gilts
Tracked from import / weaning through every stage: quarantine, weaning, farrowing, dry sow
Feed cost accumulated automatically at each stage, by batch
Imported Boars
Landing cost, quarantine and feed cost tracked from import to productive use
Monthly amortisation calculated automatically
Boar & Semen Costing
Automatically works out the actual unit cost per semen dose
Based on boar cost, feed cost and running costs
Residual Value & Fair Value
Residual value calculated automatically (e.g. at 9 months for imported sows)
Monthly amortisation posted straight into D365BC for accurate fair-value accounting
In short: cost and asset data updates in real time, giving a batch-wise view of true cost and profitability, the same view shown in the finance system.
Triple-C | NAVFARM Implementation - PMT Kick-Off Meeting
10

## Slide 12
Project Scope & Deliverables
Prudence Consulting | Phase 1 work, grouped into packages
Work Package | What It Covers
Master Data & Farm Setup | Breed master, animal register, farm/location hierarchy, silo allocation, item master, farm resources
Feed Management | Feed forecast planning & reports, automated feed cost posting
Batch & Lifecycle Management | Batch scheduling & creation, resource allocation, stage-wise entry, animal transfer traceability
Animal Health | Animal health card and full treatment history
Transfers | Transfer requests and transfer in/out between farm locations
RFID & AI Capabilities | RFID tagging, AI-driven schedules, semen production tracking, QR traceability, cost allocation
Applications & Field Capture | Web application, mobile app (online/offline), photo capture by stage
Finance & Procurement | Procurement and petty cash requisitions, integrated with D365BC
Dashboards & Reporting | Real-time dashboards, 16 standard reports, 8 custom reports
System Integration | NAVFarm Connector, D365BC stock transfer integration, biological asset module, Pig Vision integration
Note: Scope is limited to the items listed in the signed proposal. Anything extra goes through the Change Request process.
Triple-C | NAVFARM Implementation - PMT Kick-Off Meeting
12

## Slide 13
Implementation Methodology
Prudence Consulting | How we will get there, step by step
1
Project Kick-off
Formal start; team and governance confirmed.
2
Business Process Study
We study how farms and finance currently work, on-site and remotely.
3
Business Blueprint
We document and agree exactly what will be built, and both sides sign off.
4
System Configuration
NAVFarm is configured to match the signed-off blueprint.
5
Conference Room Pilot (CRP)
We walk the configured system through with your team before going further.
6
Integration & Customization
We connect NAVFarm to D365BC and Pig Vision.
7
Key User Training
Your key users are trained to use the new system.
8
User Testing
Key users test the system against real scenarios.
9
Data Migration & Go-Live Prep
Four years of historical data is loaded and checked.
10
Go-Live
The system goes live across all farms.
11
Post Go-Live Support
30 days of hands-on support to stabilise the new system.
Triple-C | NAVFARM Implementation - PMT Kick-Off Meeting
13

## Slide 14
Project Document Exchanges
What gets shared, in what format, and why
Document
Format
Purpose / When It's Used
Minutes of Meeting (MoM)
DOCX
Captures decisions and action items after each meeting
Functional Requirement / Business Blueprint (BBP)
DOCX
Documents the agreed scope, for formal sign-off
Master Data Templates
XLSX
Used to collect and load master and historical farm data
Weekly Project Report
PPTX
Shared with the PMT every week on progress and risks
Fortnightly PMO Report
PDF
Wider governance update, shared every two weeks
Report Formats Required (Customer End)
XLSX
Confirms the exact report layout Triple-C needs from NAVFarm
Change Request Form
DOCX
Used to raise and approve any change to agreed scope
Risk & Issue Log
XLSX
Tracks open risks and issues, owners and target dates
Milestone Sign-off Document
PDF
Formal sign-off at each project milestone
Additional formats may be confirmed during the Business Process Study, depending on what Triple-C's teams already use.
Triple-C | NAVFARM Implementation - PMT Kick-Off Meeting
14

## Slide 15
Implementation Timeline - Phase 1
Prudence Consulting | Kick-off on 04 August 2026
Triple-C | NAVFARM Implementation - PMT Kick-Off Meeting
15
WBS ID | Phase / Activity | Duration (Working Days) | Mode | Start Date | End Date | Comments
1 | 1. Project Kick-off | 1 | Offshore | 04-Aug-2026 | 04-Aug-2026 | Formal project launch; PMT and governance confirmed. Fixed date.
2 | 2. Business Process Study | 12 | Mix-Mode | 15-Aug-2026 | 28-Aug-2026 | On-site and remote study of current farm & finance processes (7 onshore days within this window). Fixed start date, gap after kick-off for mobilisation.
3 | 3. Business Blueprint | 7 | Offshore | 31-Aug-2026 | 08-Sep-2026 | Business Blueprint Document (BBP) prepared and signed off.
4 | 4. System Configuration & Customization (P1) | 20 | Offshore | 09-Sep-2026 | 07-Oct-2026 | Core NAVFarm configuration per signed-off BBP.
5 | 5. Conference Room Pilot (CRP) | 3 | Offshore | 08-Oct-2026 | 12-Oct-2026 | Configured solution walked through with client stakeholders.
6 | 6. Integration & Customization (P2) | 20 | Offshore | 13-Oct-2026 | 12-Nov-2026 | D365BC and Pig Vision integration build.
7 | 7. Key User Training | 7 | Onshore | 13-Nov-2026 | 20-Nov-2026 | May extend up to 5 additional days with joint management approval.
8 | 8. User Testing | 8 | Onshore | 21-Nov-2026 | 30-Nov-2026 | May extend up to 5 additional days (combined with training) with joint management approval.
9 | 9. Data Migration & Go-Live Preparation | 7 | Onshore | 01-Dec-2026 | 08-Dec-2026 | 4 years of historical data migrated (client-provided in NAVFarm template format).
10 | 10. Go-Live | 5 | Onshore | 09-Dec-2026 | 14-Dec-2026 | Production cutover.
11 | 11. Post Go-Live Support | 30 | Offshore | 15-Dec-2026 | 26-Jan-2027 | Stabilization support, performance tuning, issue resolution, user enablement.
12 | 12. Phase 2 - System Enhancement & Integration | TBD | Offshore | TBD | TBD | Scope and timeline to be finalized separately per proposal.
 | Total Phase 1 Duration (Working Days) | 120 |  |  |  | 
 | Go-Live Date | 14-Dec-2026 |  |  |  | 
 | Project Closure (Post Go-Live Support End) | 26-Jan-2027 |  |  |  | 
 | Total Calendar Span (Kick-off to Closure, days) | 176 |  |  |  | 

## Slide 16
Key Project Milestones
Prudence Consulting
Triple-C | NAVFARM Implementation - PMT Kick-Off Meeting
16
No. | Milestone | Target Date | Description / Exit Criteria
M1 | Project Kick-off Complete | 04-Aug-2026 | Project charter confirmed, PMT, governance model and communication plan agreed.
M2 | Business Blueprint Sign-off | 08-Sep-2026 | Business Blueprint Document reviewed and signed off by both parties.
M3 | Conference Room Pilot (CRP) Sign-off | 12-Oct-2026 | Configured solution demonstrated and accepted by client stakeholders.
M4 | Integration & Customization Complete | 12-Nov-2026 | NAVFarm-D365BC and NAVFarm-Pig Vision integrations built and unit tested.
M5 | Key User Training Complete | 20-Nov-2026 | Key users trained at the centralized location (Head Office).
M6 | User Testing (UAT) Complete | 30-Nov-2026 | User acceptance testing completed and signed off.
M7 | Data Migration Complete | 08-Dec-2026 | 4 years of historical pig farm data migrated and validated in NAVFarm.
M8 | Go-Live | 14-Dec-2026 | Production cutover, NAVFarm live across all farms.
M9 | Project Closure (Post Go-Live Support End) | 26-Jan-2027 | 1-month stabilization support complete, project handed to AMC/support agreement.

## Slide 17
Phase 2 - Future Enhancements
Prudence Consulting | Scope & timeline to be finalised
What Phase 2 Covers
Further process improvements on the NAVFarm platform
New reports and MIS development (NAVFarm or D365BC)
Connecting NAVFarm to water meters
Connecting NAVFarm to silo weight scales
Any other integrations, once scoped and agreed
Value It Brings
Removes manual meter and scale readings completely
Extends the same real-time visibility to new equipment and data sources
Keeps NAVFarm evolving alongside Triple-C's operations
Adds new reports and process improvements as the business needs them
Scope and effort for each item agreed with Triple-C only once confirmed
Phase 2 will be delivered off-shore, with on-site visits arranged only if required.
Triple-C | NAVFARM Implementation - PMT Kick-Off Meeting
17

## Slide 18
Roles, Governance and Communication (1 of 2)
Group Finance Director
Governance Structure
Three-tier governance model: Client and Implementation Partner
Director-level kickoff, then regular PM meetings
Project Manager meetings held weekly
Steering Committee meetings held monthly
Standing Committee convened for escalations, as needed
PMO Oversight Areas
Vendor Management
ERP vendor assessment, RFP & contracting, SLA and commercials
Risk & Change Management
Risk assessment, change request control, scope governance
Implementation Oversight
Project planning, milestone tracking, issue resolution
UAT & Go-Live Readiness
UAT management, data validation, handover & transition
Triple-C | NAVFARM Implementation - PMT Kick-Off Meeting
18

## Slide 19
Roles, Governance and Communication (2 of 2)
Group Finance Director
Communication & Reporting
Weekly status reports: activities, risks, schedule/cost impact
Fortnightly PMO reports for wider governance visibility
Regular project status reporting against the plan (% complete, RAG status)
Change requests managed via formal sign-off on scope, timeline and cost
Documentation Repository (Microsoft Teams)
All project documents held centrally in Microsoft Teams
Organised by stage: Initiation, Planning, Execution, Monitoring & Control, Closing
One shared source of truth for both teams throughout the project
Escalation Path
Support Team → Project Manager → Project Management Office (PMO) → Project/ Operation Director
Triple-C | NAVFARM Implementation - PMT Kick-Off Meeting
19

## Slide 20
Operational Considerations & Risk Management (1 of 2)
a) Biosecurity Considerations
Johan Odendaal
Device and mobile app use on farm - clear hygiene protocols needed
Access control for field data capture teams entering different farm zones
RFID tag application and equipment handling near livestock
Cleaning and disinfection routine for devices shared between sheds
Alignment with existing farm biosecurity procedures and visitor protocols
Confirm whether any devices should be dedicated to a single farm/shed
b) Farm Workflows & Inputs
John Nyabadza
Map current daily/weekly farm data capture workflows, farm by farm
Confirm offline data capture needs where connectivity is limited
Review how feed, health and mortality data is currently recorded
Identify who captures data today, and who will do so in NAVFarm
Agree how paper/Excel records will transition to digital entry
Align these workflows with the NAVFarm process design during the Business Process Study
Triple-C | NAVFARM Implementation - PMT Kick-Off Meeting
20

## Slide 21
Operational Considerations & Risk Management (2 of 2)
Project risk register for discussion
Risk | Why It Matters | How We'll Manage It
Farm connectivity gaps | Some farms may have limited internet access | Offline data capture in the NAVFarm mobile app, syncing when connected
Data migration accuracy | 4 years of historical data must be clean and correctly formatted | Data provided in NAVFarm template, validated before go-live
User adoption | Staff used to paper/Excel may resist new digital workflows | Farm champions, structured training, clear change communication
Timeline dependencies | Delays in data, approvals or feedback affect the plan | Weekly status reporting and early escalation via PMO
Biosecurity exposure | New devices and field visits near livestock | Hygiene protocols agreed with farm management before rollout
Scope creep | Ad hoc requests outside the signed proposal | Formal Change Request process for anything beyond agreed scope
Triple-C | NAVFARM Implementation - PMT Kick-Off Meeting
21

## Slide 22
Resource Allocation & Organisational Change Management (1 of 2)
Group Finance Director
Resource Allocation
Timely access to data, users and infrastructure is Triple-C's responsibility
Key user availability is required for training and testing (15 days)
IT resources needed for integration and data migration support
Farm-level champions needed at each site for rollout
Change Management
HR involvement in adoption planning (Human Capital role)
Clear communication of new digital workflows to farm teams
End-user training beyond key users available at extra cost
Delays in approvals, data or feedback may push out timelines
Triple-C | NAVFARM Implementation - PMT Kick-Off Meeting
22

## Slide 23
Resource Allocation & Organisational Change Management (2 of 2)
How Triple-C can start preparing, from today
1
Share the project vision and goals with all farm and finance teams, the earlier people understand 'why', the easier adoption will be
2
Nominate a change champion at each farm to support colleagues through the transition
3
Start gathering and organising current records - feed sheets, health cards, registers - ready for the Business Process Study
4
Begin the mindset shift from paper/manual entry towards structured, digital data capture
5
Check connectivity and device availability at each farm, and flag any gaps early
6
Block key users' calendars in advance for training and testing (15 days)
7
Set up a simple internal point of contact or FAQ for project questions
8
Involve HR early to align roles, expectations and any job description changes
Triple-C | NAVFARM Implementation - PMT Kick-Off Meeting
23

## Slide 24
Immediate Next Steps (1 of 2)
Prudence Consulting | What happens right after this meeting
# | Step | What It Involves | Owner
1 | Detailed Process Study | Prudence to study Triple-C's farm and finance processes end-to-end, on-site and remotely. | Prudence
2 | Current Process Review | Document how feed, health, breeding and mortality are tracked today, at each farm. | Joint
3 | Current Reporting Structure Review | Review existing reports and MIS: who receives what, and how often. | Joint
4 | Roles Review | Confirm each PMT and farm member's role and time commitment for the project. | Triple-C
5 | Finalise Business Process Study Schedule | Agree dates for farm visits and stakeholder interviews. | Joint
Triple-C | NAVFARM Implementation - PMT Kick-Off Meeting
25

## Slide 25
Immediate Next Steps (2 of 2)
Prudence Consulting
# | Step | What It Involves | Owner
6 | Data Import Templates | NAVFarm-format templates to be shared with Triple-C for master and historical data. | Prudence
7 | Current Input Documents | Collate existing Excel sheets, data cards, log books and registers used across farms. | Triple-C
8 | Master Data Formats | Confirm breed, location, item and animal register formats ahead of the Business Process Study. | Joint
9 | Farm Site Visits | Prudence team to visit farms to observe day-to-day operations first-hand. | Prudence
10 | IT & Infrastructure Readiness Check | Confirm devices, connectivity and offline data capture needs at each farm. | Triple-C
11 | Confirm Change Request Process | Agree the formal Change Request process and pricing before Blueprint sign-off. | Joint
Triple-C | NAVFARM Implementation - PMT Kick-Off Meeting
26

## Slide 26
Any Other Business
Thank you - next PMT meeting to be confirmed.
Project Manager (Prudence): Paul Young | paul.young@navfarm.com
PMT Chairperson (Triple-C): Mandy Murebwa, Group Finance Director