## Scheduler
Project Triple-C Weekly Scheduler (20 Aug – 25 Aug 2026)
# | Open Item | Details | THU (20-Aug) |  | FRI (21-Aug) |  | SUN (23-Aug) |  | MON (24-Aug) |  | TUE (25-Aug) |  | Owner
|  |  | Status | Notes / Time | Status | Notes / Time | Status | Notes / Time | Status | Notes / Time | Status | Notes / Time
1 | Pig Costing Discussion |  | Scheduled
2 | Discussion on T-C Data Set / Reports Received | [5 empty] | Scheduled | 2pm – 5pm
3 | Master Data → Discussion + KPI |  | Scheduled | Porta Farm 8:30 to 01:00 PM
4 | MoM's Final | 1st T-C Responsibility | [6 empty] | In Progress
5 | Farm - Process Discussion | Mr. Johan → sow selection & Tagging & Green -> Blue -> Yellow |  |  |  |  | Scheduled | 2pm – 5pm | Scheduled |  |  |  | Mr. Johan
6 | Set of Data Final → Pigvision App (Integration) Discussion |  |  |  | Scheduled
7 | Historical Data - Final | Templates |  |  | Scheduled
8 | Gap List → Logistics Module |  | Due | Submit gap fitment doc with effort |  |  |  |  | Scheduled | Tripel-C have to confirm
9 | QC Module |  | Due | Submit gap fitment doc with effort |  |  |  |  | Scheduled | Tripel-C have to confirm
10 | Sale's Points |  | Due | Submit gap fitment doc with effort |  |  |  |  | Scheduled | Tripel-C have to confirm
11 | GRN → NAV Farm |  | Due | Submit gap fitment doc with effort |  |  |  |  | Scheduled | Tripel-C have to confirm
12 | Other Expenses Voucher + Their Inegration with D365BC |  | Due | Submit gap fitment doc with effort |  |  |  |  | Scheduled | Tripel-C have to confirm
13 | BRP - Draft (Round Table) | with Management & Stakeholders | [8 empty] | Scheduled | Review meeting
Legend:
|  | Completed |  | In Progress |  | Scheduled |  | Due |  | Blocked |  | Not Started