## Week 1 WBS Schedule
.
Work Breakdown Structure (WBS) — Week 1
Schedule: 17 Aug 2026 (Mon) to 21 Aug 2026 (Fri) ¦ Daily pickup 8:00 AM
Office Session |  | Farm Session |  | Logistics |  | Fields to fill in
WBS ID | Day / Date | Time | Activity / Task / Workshop | Location | Required (Triple C) | NavFarm Team Members Assigned | Triple C Team Members Assigned | Status | Remarks
STAGE 0: FARM VISIT
0.1 | Saturday 15 Aug 2026 | 10:30 AM - 2PM | Farm Visit | Farm | Porta farm | Abhinav, Mukul, Paul | Mr. Jimmyson &. Mr. Hama | Completed | Need all templates and reports and other documents soft copy to be mailed to anshu.kumar@navfarm.com
STAGE 1: BREEDING
1.1 | Monday 17 Aug 2026 | 9AM - 2PM | Breeding – Selection of sows | Office | Tepmlates, Reports, KPI, Health, Vaccination, Medication, Weight, Growth, Boar & Sow Selection, Heat Detection, Breeding KPI Reports, Timeline | Abhinav, Mukul, Paul | Johan Odendaal |  | Need all templates and reports and other documents soft copy to be mailed to anshu.kumar@navfarm.com
STAGE 2: GESTATION
1.2 | Monday 17 Aug 2026 | 9AM - 2PM | Gestation – Pregnancy period of the sow | Office | Tepmlates, Reports, KPI, Health, Vaccination, Medication, Weight, Growth, Boar & Sow Selection, Heat Detection, Breeding KPI Reports, Timeline | Abhinav, Mukul, Paul | Johan Odendaal |  | Need all templates and reports and other documents soft copy to be mailed to anshu.kumar@navfarm.com
STAGE 3: FARROWING
2.1 | Tuesday 18 Aug 2026 | 9AM - 2PM | Farrowing – Sow gives birth to piglets. | Office | Tepmlates, Reports, KPI, Health, Vaccination, Medication, Weight, Growth, Boar & Sow Selection, Heat Detection, Breeding KPI Reports, Timeline | Abhinav, Mukul, Paul | Johan Odendaal |  | Need all templates and reports and other documents soft copy to be mailed to anshu.kumar@navfarm.com
STAGE 4: LACTATION / SUCKLING
2.2 | Tuesday 18 Aug 2026 | 9AM - 2PM | Lactation / Suckling – Piglets remain with the sow and consume milk. | Office | Tepmlates, Reports, KPI, Health, Vaccination, Medication, Weight, Growth, Boar & Sow Selection, Heat Detection, Breeding KPI Reports, Timeline | Abhinav, Mukul, Paul | Johan Odendaal |  | Need all templates and reports and other documents soft copy to be mailed to anshu.kumar@navfarm.com
STAGE 5: WEANING
3.1 | Wednesday 19 Aug 2026 | 9AM - 2PM | Weaning – Transition from depending on the sow's milk to becoming an independent feeder. | Office | Tepmlates, Reports, KPI, Health, Vaccination, Medication, Weight, Growth, Boar & Sow Selection, Heat Detection, Breeding KPI Reports, Timeline | Abhinav, Mukul, Paul | Johan Odendaal |  | Need all templates and reports and other documents soft copy to be mailed to anshu.kumar@navfarm.com
STAGE 6: NURSERY / CREEP STAGE
3.2 | Wednesday 19 Aug 2026 | 9AM - 2PM | Nursery / Creep Stage – Young piglets are provided specialized feed and management after weaning. | Office | Tepmlates, Reports, KPI, Health, Vaccination, Medication, Weight, Growth, Boar & Sow Selection, Heat Detection, Breeding KPI Reports, Timeline | Abhinav, Mukul, Paul | Johan Odendaal |  | Need all templates and reports and other documents soft copy to be mailed to anshu.kumar@navfarm.com
STAGE 7: GROWER STAGE
4.1 | Thursday 20 Aug 2026 | 9AM - 2PM | Grower Stage – Pigs grow rapidly and transition to higher-volume feed. | Office | Tepmlates, Reports, KPI, Health, Vaccination, Medication, Weight, Growth, Boar & Sow Selection, Heat Detection, Breeding KPI Reports, Timeline | Abhinav, Mukul, Paul | Johan Odendaal |  | Need all templates and reports and other documents soft copy to be mailed to anshu.kumar@navfarm.com
STAGE 8: FINISHER STAGE
4.2 | Thursday 20 Aug 2026 | 9AM - 2PM | Finisher Stage – Pigs are raised to market/slaughter weight. | Office | Tepmlates, Reports, KPI, Health, Vaccination, Medication, Weight, Growth, Boar & Sow Selection, Heat Detection, Breeding KPI Reports, Timeline | Abhinav, Mukul, Paul | Johan Odendaal |  | Need all templates and reports and other documents soft copy to be mailed to anshu.kumar@navfarm.com
STAGE 9: REPLACEMENT BREEDING STOCK
5.1 | Friday 21 Aug 2026 | 9AM - 2PM | Replacement Breeding Stock – Selected gilts are retained to replace older breeding animals. | Office | Tepmlates, Reports, KPI, Health, Vaccination, Medication, Weight, Growth, Boar & Sow Selection, Heat Detection, Breeding KPI Reports, Timeline | Abhinav, Mukul, Paul | Johan Odendaal |  | Need all templates and reports and other documents soft copy to be mailed to anshu.kumar@navfarm.com
STAGE 10: GILTS
5.2 | Friday 21 Aug 2026 | 9AM - 5PM | Gilts – From Week 4 until Insemination | Office | Tepmlates, Reports, KPI, Health, Vaccination, Medication, Weight, Growth, Boar & Sow Selection, Heat Detection, Breeding KPI Reports, Timeline | Abhinav, Mukul, Paul | Johan Odendaal |  | Need all templates and reports and other documents soft copy to be mailed to anshu.kumar@navfarm.com
STAGE 11: SERVICE LANE
5.3 | Friday 21 Aug 2026 | 9AM - 5PM | Service Lane- Process | Office | Tepmlates, Reports, KPI, Health, Vaccination, Medication, Weight, Growth, Boar & Sow Selection, Heat Detection, Breeding KPI Reports, Timeline | Abhinav, Mukul, Paul | Johan Odendaal |  | Need all templates and reports and other documents soft copy to be mailed to anshu.kumar@navfarm.com
STAGE 12: Costing & Amortization
5.3 | Friday 21 Aug 2026 | 9AM - 5PM | Costing & Amortization | Office | Discussion on the current financial process for capitalization and amortization of biological assets throughout the breeding cycle, along with consumable assets during weaning and growing stages. The discussion will also cover batch creation and structure, litter lineage, and the feed tracking mechanism, including batch-wise and animal-wise feed consumption, cost allocation, and FCR monitoring, with a focus on maintaining accurate financial records and ensuring proper cost allocation throughout the production cycle. | Abhinav, Mukul, Paul | John Nyabadza |  | Need all templates and reports and other documents soft copy to be mailed to anshu.kumar@navfarm.com